## Sheet1
ID | Title | Functional Area | Implementation Phase | Target Date | Who? | Data Comments | Data Impact | Workstream | Requester | Functional Area 2 | Owner (RMIT) | Owner (Vendor) | Category | Primary System | Secondary System | Status | Change Control Description | Change Control Justification | Legislative or Regulatory Requirement | Priority | Integration Impact | Reporting Impact | Process and Services Impact | Cross-functional Impact | Schedule Impact | Cost Impact | Testing Impacts | Decision Required By | Decision Date | PMO decision notes | Phase | Stage | Created Date | Level of Governance | Contract CR Reference | Comment
1 | Recruitment and Onboarding Configuration Workbooks | Recruitment | NA |  |  |  | None | HR | x | None | Renee Teranen | Michael Currie | Scope | Workday | None | Approved | Request to use updated configuration workbooks for P2 build | The updated configuration workbook for the P2 build reflects final state and there will be no cross functional domain impacts caused by using the updated configuration workbooks as these sheets have not been altered | FALSE | Medium | None | Contingent management reports identified to support time entry compliance and cross functional reporting. | New role (Contingent Worker Coordinator) will support recruiting / contracting / ending CWs. No changes to Core HR processes, routing for Cws will follow the same flow as Employees | Contingent cross functional report as outlined above. Project sessions / working groups required to ensure this end to end process has been agreed by both HR, Procurement and Finance. | No impact to schedule, can be included in P2 build timelines. | None |  |  | 2020-02-10 | Raised & approved at 10/02 Change Control Meeting. ​ | Phase 2 | Prototype 2 | 2020-01-13 | Program | 652827
2 | Jobs on campus descoped from SAMS and WD Integration | Recruitment | NA |  |  |  | None | HR |  | None | Renee Teranen | Michael Currie | Scope | Workday | SAMS | Approved | Support Jobs on Campus (Student Data Load) functionality without an integration | As a result of the decision to de-scope the SAMS to WD integration, functionality (custom field, questionnaire data, application form, reporting) will need to be built (configured) to support the requirements for Jobs on Campus | FALSE | Medium | None | Yes - Questionnaire reporting will need to be developed | None | None | Can be absorbed in current P2 timeline, so no impact | None |  |  | 2020-02-10 01:00 | Raised & approved at 10/02 Change Control Meeting | Phase 2 | Prototype 2 | 2020-01-13 | Program | 651624
3 | EBA Configuration Split | HCM Core | SIT1 | 24/05/2020 |  | Already addressed in SIT1 Crosswalk. CR is complete. | Data will need this to map employees to the EBA in Workday | HR |  | Absence and Time | Renee Teranen | Michael Currie | Scope | Workday | Downstream Systems | Approved | One EA Agreement type was missed in the configuration workbook for segregating employees into Academic and Professional | No clear employee subgroup identifier in Workday, but this needs to be broken down into professional or academic employees specifically for RMIT Online who has only one (1) group of employee grouping | TRUE (must explain in Change Control justification) | High | Integrations will need to update all integrations that reference collective agreements (most importantly the Blueprint for ADP). Mathew has been versed and no major impacts | Reporting will need to include this CA in all reports that reference collective agreements | None | Payroll (ADP) to be across the change, see attachment | Can be absorbed in current schedule timeline for P2 | None |  |  | 2020-02-10 01:00 | Raised & approved at 10/02 Change Control Meeting | Phase 2 | Prototype 2 | 2020-01-13 | Program | 650972
4 | RMIT VN - Time in Lieu Time Off Unit Change (Days to Hours) | Absence and Time | SIT1 | 24/05/2020 |  |  | Y | HR |  | Payroll | Renee Teranen | Michael Currie | Scope | Workday | Payroll | Approved | Time in lieu time off unit needs to be changed from days to hours | ADP configuration has TIL captured in hours not days. Vietnam has confirmed this is correct and needs to be configured for their entity | TRUE (must explain in Change Control justification) | High | None | None | Y | Impact to payroll, the ADP solution has already had a CR raised to align with this requested change. | None | None |  |  | 2020-02-24 | 24/2/20 Approved. Raised at 10/02 CCM. Follow up discuss required to ensure that time units are configured consistently in WD and ADP. Raised at 17/2 CCM. Discuss with Data. 24/2 Eric advised no impacts. | Phase 2 | Prototype 2 | 2020-01-13 | Program | 650523
5 | Recruitment and Onboarding Configuration WB - Contingent Worker BP | Recruitment | NA |  |  | Recruitement is not in scope for Data Conversion. Need more information | See Attachment | HR |  | Procurement | Renee Teranen | Michael Currie | Scope | Workday | None | Approved | Requirements: 1. Add New Security Group - Contingent Co-ordinator 2. At point of Contract CW - initator to be Contingent Co-ordinator 3. At point of Contract CW - approver to be Cost Centre Manager 4. At Create PO - action by Contingent Co-ordinator 5. Cr | Cross functional session enabled refinement of the end to end solution for P2 build and agreement on changes to initiators and approvers to enable more efficient and seamless flow | FALSE | High | See Attachment | See Attachment | See Attachment | See Attachment | None | None |  |  | 2020-02-17 01:00 | Approved & Endorsed 17/2/20. Raised at 10/02 Change Control Meeting. Follow up discussion required with Procurement work stream to ensure cross functional alignment. | Phase 2 | Prototype 2 | 2020-01-13 | Program | 651625
6 | Additional Work Schedule (Absence and Time) | Absence and Time | SIT1 | 24/05/2020 | Ken/Eric | Need inputs from ADP to create additional work schedule --> Workday --> Mapping Timelines are dependant on ADP design. May not achieve SIT2 timelines. Complete | Significant | HR |  | Payroll | Renee Teranen | Michael Currie | Scope | Workday | ADP | Approved | Additional work schedules have been identified that require creation in Workday. The reason for the CR being raised is the number of additional work schedules that is being identified, which is already vastly greater than the agreed amount in the SoW | Workday (Absence and Time) and ADP require work schedules to accurately pay employees | FALSE | High | N | None | None | Significant - ADP | None | None |  |  | 2020-02-10 01:00 | Raised & approved at 10/02 Change Control Meeting | Phase 2 | Prototype 2 | 2020-01-13 | Program | 649891
9 | Removal of Casuals from all T&P Processes | Talent | NA |  |  |  | Will eliminate manual processing requirements of the payroll team. | HR |  | Payroll | Gary Adamson | Michael Currie | Integration | Workday | ADP Payroll (SAP) | Cancelled | Review the option of automating and integrating most of the HR & Payroll processes that are part of managing employees that have multiple positions. | Eliminate manual process steps of employees who have multiple positions. Provide the foundation of automation and predicted future growth of employees with multiple positions. | FALSE | Medium |  | Reports are required to validate employees who hold multiple positions. | There is process impacts depending if management of employees who hold multiple positions are performed manually or is automated |  | Will be analysed during review - automation testing would not be available until SIT phase. | There will be a cost impact, actual cost are being investigated |  |  |  | The teams are investigating and analysing the effort, cost and project impacts to enable RMIT business to confidently decide on teh continuation of this Change Request. | Phase 2 | SIT | 2020-01-16 |  |  | ML 12/03:- No integration will be built as per decision by Michael V. Please see attached email from Renee
10 | Ease into retirement configuration | HCM Core | SIT2? | 05/06/2020 | Ken | Ken to check with Snehal and request more information | No data impacts | HR |  | Performance | Renee Teranen | Michael Currie | Scope | Workday | None | Approved | Update Talent and Performance processes to remove casuals | During P1 a decision was made include Systematic and Regular Casuals in all Talent and Performance processes. However, it has been confirmed, identifying and segregating casuals is not possible resulting in removing Casuals from the T&P scope. | FALSE | Medium | No integration impacts | No reporting impacts | Comms that talent and performance will not be conducted for casuals. This has been passed to the TnC team, please see attached email | No impacts cross functionally | None | None |  |  | 2020-02-17 01:00 | Raised and approved at 17/02 Change Control Meeting | Phase 2 |  | 2020-01-16
11 | VN - Primary termination listing changes | HCM Core | SIT2 |  |  | Requires a new extract | Identify those currently on ‘ease into retirement’ fixed term contract. Eric/Ken are across this requirement and there are no major impacts, see attachment | HR |  |  | Renee Teranen | Michael Currie | Process | Workday |  | Approved | Ease into retirement option for employees is captured currently on a form, staff get 2 options to choose from and Payroll processes this request in SAP currently. We have analysed this form and will be catering the solution on workday | It was brought to us quite late post the sign off & we had to analyse the requirements to understand how we cater for it. Our current job change process will be used | FALSE | High | This was raised by the payroll team and ADP integration is in place for our job change/termination processes. Please see attachment | Current reporting which has been built will cater for this change | Recording of ease into retirement via a new contract type. Snehal to consult with Workplace Relations around the categorisation of an individual on an ‘ease into retirement’, they are not identifiable I believe. Only HR will be able to see these employees | Potential security impact on visibility of those on an EIR agreement. Payroll will be impacted as they currently manually process all of these cases, see attachment | None | None |  |  | 2020-02-24 | 24/02/20 - Endorsed and approved. Raised at 17/02 Change Control Meeting. Put on hold. Follow up discussion between HR & Data to be had. Eric approved from Data 24/2/20 | Phase 2 | Prototype 2 | 2020-01-17
12 | Finance Approval Step in Recruiting and Comp BPs | Human Resources | NA |  |  |  | Potential mapping requirements to these primary termination reason types (however this will just be changing a referenced field). So no major impacts as they will be pulling the data as per SAP | HR |  |  | Renee Teranen | Michael Currie | Data | Workday | ADP-Payroll | Approved | Refined list of VN primary term reasons, to make it a global list with some hard errors on two (2) reasons to be VN specific i.e. adding new contract, no offer and new contract: turn down offer to the list and removing all other VN local reasons from P2 | Vietnam originally had local termination reasons, which through discussions post sign off has evolved and we have now made 1 global primary reason termination list and simplified the design | FALSE | Medium | All integrations that reference termination and local termination will require review. I believe this to only currently impact the ADP blueprint documentation. This requirement came from integration team to change. | Simplified reporting globally however reporting will need to assess the impact on any termination reports for Vietnam/Aus and Spain. ALl reporting is based on primary and secondat reasons so no major issues. | The process will remain the same and no services impacts | Payroll will be receiving primary termination reason only from a WD perspective. Validations required in Core HR to ensure that AU and SP cannot select the 2 Vietnam reason codes (this will cause issues with integration). This will be configured in WD | None | None |  |  |  | Changes the list in config workbook post CR approval. Raised at 17/02 Change Control Meeting. Deferred as requires conversation between HR & Data. Data team has been versed and this request has been validated that there is no major impacts (see attachment | Phase 2 | Prototype 2 | 2020-01-20 | Workstream
13 | Integration - CVCheck | Recruitment and Onboarding | NA |  |  |  | No impact as this is configuration | HR | Renee | Finance | Renee Teranen | Michael Currie | Scope | Workday |  | Approved | Due to the unavailability of the budget check staffing functionality, Finance is requesting an approval by a Compensation Finance Partner security role for the various HCM processes | Change will allow for financial governance on HR processes that are related to budget impact | FALSE | Medium | No impacts as this is configuration | No impact as this is configuration | No impact as this is configuration | Finance security role to be included within some HR processes. This will involve the applicable training for this security role. | No impact as this will be a simple change embedded into the SIT build | No cost impact | Testing team will review and make updates - this change will be accomodated. | 2020-03-16 | 2020-03-16 | Pending endorsement from VCE (Feb 2020) and Council (Jun 2020) . Risk has been raised in PMC (660977) | Phase 2 | UAT | 2020-01-21 | PCG | 650493 | Meeting held on 09/01 with Finance. All in agreement to implement approval workflow changes as per attached spreadsheet. 16/03 - approved by CR review group. consider business process impacts and bottlenecks.
15 | Academic Appointment - Missing Type | HCM Core | TBD | 05/06/2020 | Kathleen | Kath to request more information | No impact to data stream | HR |  |  | Renee Teranen | Michael Currie | Integration | Workday |  | Approved | An integration is required between Workday and CV Check to ensure that appropriate employment checks are conducted in ensuring a high quality of talent is brought into RMIT and retained | The background/employment check process is an area highlighted as a HR objective and without this integration RMIT is exposed to higher levels of risk if not implemented. Based on volume of checks manual processing is not a viable workaround. | FALSE | Medium | The integration team will need to include this as part of their integration inventory. Technical specifications have been supplied by CVCheck. | No impact to reporting stream | No impact to process and services stream | No impact to cross functional stream | No impact to schedule | No impact to cost |  |  | 2020-02-24 | 24/2/2020 Endorsed&Approved. ApprovThis has been presented to integration team as well as Michael V for inclusion into the integration inventory. Raised at CCM 17/2. 24/2/20 CCM - Manish advised part of integration scope. Sonia advised test after go live. | Phase 2 | UAT | 2020-01-24 | Program | 654141
17 | Vietnam supervisory org setup for WD | HCM Core | NA |  |  |  | There will need to be segregate the academic affiliate from the Non Sal group. These are easily identifiable | HR |  |  | Renee Teranen | Michael Currie | Integration | Workday |  | Deferred | The Workday system will house specific data for the Academic Affiliates cohort. There are specific third party systems that need to consume this data and as such the Change Request is to cover the integration to be built to cater for this. | Currently there are specific third party systems that consume Academic Affiliate data from the legacy SAP system, and this needs to continue with the golive of Project Pi. | FALSE | Medium | There will need to build two (2) integrations to support academic appointment functionality | No reporting impacts as the reports currently exist in the standard suite | The team wil need to commuicate the model of who will support and manage academic functionality in Workday | No impacts to other functions | No impact to schedule | No impact to cost |  |  |  | Integration and HR stream to make a decision on whether the required integrations will be built | Phase 2 | Build | 2020-01-24 | Program
20 | Academic Affiliates - Visa Requirements | Academic Appointments | SIT1 | 24/05/2020 |  | Requires data cleansing in source. Currently 76 records have AU citizenship, 4 have overseas citizenship and 600+ have no information. | No data impacts | HR |  |  | Renee Teranen | Michael Currie | Scope | Workday |  | Approved | Academic Affiliate Type missing from configuration (Vice Chancellor’s Innovation Professor) | Need to ensure the correct mapping of Academic Appointments within RMIT | FALSE | Medium | No integration impacts | No reporting impacts | No process and services impacts | No cross-functional impacts | No schedule impacts | No cost impacts |  |  | 2020-02-17 01:00 | Endorsed & Approved 17/2. Change request to be approved by change control board. Raised at 17/02 Change Control Meeting | Phase 2 | SIT | 2020-01-24 | Program
21 | Work Schedule updates - Align with ADP Changes | Absence and Time | SIT1 | 24/05/2020 | Ken/Eric | Need inputs from ADP to create additional work schedule --> Workday --> Mapping Timelines are dependant on ADP design. May not achieve SIT2 timelines. Complete | No impact | Finance |  | HR | Natalia Hawkins | Aneta Wielgus | Process | Workday | Service Access (ServiceNow) | Closed | For Nov go-live the Academic Affiliates will be paid via ad hoc payment process. AA will submit their expenses vi ServiceNow form to be approved by the Cost Center Manager. When approved Finance will process as ad hoc payment with the approval of CFO. | Aim to change policy to enforce the process that if Affiliates are eligible for claiming expenses, they will claim it to their home institution (e.g. Uni) and the the institution will invoice RMIT. This will be added to Fit Gap report. | FALSE | Medium | No imapct | No impact | ServiceNow workflow to be designed | No impact | No impact | No impact | Process needs to be tested | 2020-03-20 | 2020-03-11 | Include in P2 design. Natalia to raise the need for policy changes with COO and CFO. | Phase 2 | Prototype 2 | 2020-01-29 | Program
22 | Migration of Compliance Courses Completions from SAP and Bridge to Workday | Talent | SIT2 | 03/06/2020 |  | The data is loaded into RMIT9 | Low impact | HR |  |  | Renee Teranen | Michael Currie | Data | Workday |  | Approved | Due to reporting lines for some staff in Vietnam running into Managers in Australia, to service the unit with accurate security roles the split of org needs to occur. | The split of units should not impact any configuration or data. | FALSE | High | No Impact | Low impact | No impact | No impact but we will need to communicate to all other leads outside HR. | No Impact | No Impact |  |  | 2020-02-24 | 24/2/20 CCM Endorsed & Approved.splitting the org unit where we have Vietnam and Australian executives currently in one unit. | Phase 2 | Prototype 2 | 2020-01-29 | Workstream
23 | VN-P2-CRs-Time & Absences | Absence and Time | NA |  |  |  | No | HR |  | Security | Renee Teranen | Michael Currie | Security | Workday |  | Cancelled | HCM Workday security roles may need to be amended to fit the future state processes |  | FALSE | Medium | No | Yes | Yes | No | [5 empty] | 1. Provide process to role mapping spreadsheet; 2. Complete impact analysis of spreadsheet; 3. create plan on when & how to execute in time for SIT; 4. update process maps/ workbooks post P2 | Phase 2 | Prototype 2 | 2020-02-03 | Workstream |  | Please see attached email. This would be addressed by post P2 workbook sign off work which needs to be completed by the Services team.
25 | Workday / ADP integration - annual salary amount | Compensation | NA |  |  |  | There will be no impacts to the data stream | HR |  |  | Renee Teranen | Michael Currie | Integration | Workday | NetIQ | Deferred | In Workday there are no Web Services to bring from NetIQ the Academic Appointments (employees) email and enumber to WD | Requirement to bring from NetIQ Academic Appointment (employee) email and enumber into Workday to support downstream systems which may rely on this data e.g. SAMS | FALSE | High | Yes - The integration team will need to assess how NetIQ will supply the email and enumber into WD to support downstream systems such as SAMS. An options paper has been prepared by HR (see attached) | There will be no impacts to the reporting stream | There will be impacts to the process and services stream but this is dependent on the proposed solution by the integration team | There will be no impacts to the cross functional stream | There will be no impacts to the schedule | There will be no impacts to the cost |  |  |  |  | Phase 2 |  | 2020-02-04
26 | Timing of delivery for Finance and Procurement Cross-Functional Reports | Reporting | NA |  |  |  | Citizenship will be required along with the visa information. This data has already been converted by Data team | HR |  | Reporting, Data | Renee Teranen | Michael Currie | Scope | Workday |  | Approved | Through a discussion with the BAU contracts team, additional requirements were highlighted around visa requirements for the academic affiliates. Affiliates in some cases require visas, in which RMIT provide sponsorship. | Updates are required to the appointment BP's to ensure review steps and reports are leveraged to track these individuals. If affiliates are working at RMIT without a visa, they are breaking immigration law. | TRUE (must explain in Change Control justification) | High | No integration impact | Reporting will be required to track individuals with expired visas. Reporting requirement email attached | BAU team will need to monitor and track these individuals through reports and communicate with the academic partner | Please see reporting and data impacts | None | None | Additional scenario to be tested in SIT | 2020-03-23 |  | Decision has been taken by HRSLT to keep the process as is i.e. manual process. Config and process workbooks have been updated and will be configured in for SIT | Phase 2 | SIT | 2020-02-04 | Workstream
30 | De-scoping ADP Streamline payroll solution for RMIT Spain | Compensation | NA |  |  |  | Remapping of original schedule ID to new schedule ID | HR |  | Payroll | Renee Teranen | Michael Currie | Data | Workday | ADP | Approved | There is a misalignment between Workday and ADP. This is attributed to ADP naming convention changes and genuine typo's. | The Work Schedule ID is used by Workday and ADP, and therefore must be in sync. |  | High | Nil | No impact to reporting team | No impact to process and services team | No impacts to other streams as WD will need to align to ADP | No impact to schedule. Will be done in preparation for SIT | No impact to cost |  |  | 2020-02-24 | 24/2/20 - Endorsed & Approved CCM. All variations in work schedules to be identified, verified and updated in either Workday, ADP, or both, to align both systems. Raised at 17/02 Change Control Meeting | Phase 2 | SIT | 2020-02-07 | Program
48 | Capture passport information for dependent | HCM Core | TBD |  |  |  | As described in change control justification | HR |  |  | Renee Teranen | Michael Currie | Data | Workday | SAP and Bridge | Approved | Compliance Courses completions for last two years to be migrated to Workday Talent | Compliance courses have to be re-taken based on the refresher requirements of 2 years. This is the regulatory requirement. To track two years completions, this data is required to be migrated from SAP and Bridge. Eric is aware of this. | TRUE (must explain in Change Control justification) | High | No impact to integration | No impact to reporting | No impact to process and services | No impact to other streams | No impact to schedule | No impact to cost |  |  | 2020-02-24 | 24/2/2020 Endorsed & Approved CCM - Data migration needs to take place for these training records. Eric is across the requirement (see attached). In addition data validation needs to occur to ensure that the right data is being migrated. Raised at 17/02 C | Phase 2 | Prototype 2 | 2020-02-07 | Program
49 | Defer go live date for the icertis Source to Contract | Procurement (Sup Contract, RFQs) |  |  |  |  | No Impact on Data - confirmed by Ruhi | HR |  |  | Renee Teranen | Michael Currie | Data | Workday | ADP | Approved | After P2 workshop for VN, couple of things have been identified and discussed and got approved for raising CRs for VN. | The details of CRs is attached. | FALSE | High | No impact from payroll, !/2 day impact expected for integrations for this CR, please see attachments. | Reporting will need to reflected in hours rather than days - Confirmed okay by Rafay | Employees will see entitlements in hours not days - Confirmed okay by Michelle P | Payroll needs to review all calculation formulas related to leaves - Confirmed ok By Chi | No impact to schedule | No impact to cost |  |  | 2020-03-16 | Ensure this requirement is in line with Vietnam legislation and with the absence and time stream. WD stores information in days whereas in ADP (GV) it is stored in hours. This affects both AU and VN configuration | Phase 2 | SIT | 2020-02-10 | Program | Not applicable | JE: PMO: CR approved by group 16/03 ML 12/03:- Pending updates from Wendy and Chi on this CR to send across for formal approval
50 | 15 x New Time Entry Codes - VNM | Absence and Time | NA |  |  |  | n/a | HR |  | Payroll | Gary Adamson |  | Integration |  | Workday | Approved | ADP to amend configuration to convert the annual salary to a fortnightly value in line with the pay cycle | alignment of Workday and ADP configuration to ensure correct payment of AU employees | FALSE | High | Workday is storing salary as an annual amount and PECI has been configured to pass this to ADP GlobalView - this is not required to be changed | n/a | n/a |  | can be absorbed by ADP to be included in the ADP UAT | n/a |  | 2020-02-24 | 2020-02-24 | Endorsed & approved 24/02/2020 - impact assessment to be completed by HR, Payroll and Technology teams | Phase 2 | Build | 2020-02-14 12:52 | Program | ADP 9037206
54 | Creating New Cost Centers from G2 integration | Payroll | NA |  |  |  | None | Reporting |  | Cross-Functional (Workday Fin / Proc plus other sources) | Eric Hoffman | Simon Biddle | Reporting | Workday | ICertis & others | Approved | Due to ICertis ODS implementation timelines and possible changes to Fin / Proc Cross-Functional Reporting Inventory (exp 10-Mar), deliverables for Functional Specs and Build would be delayed. These activites will now be done during SIT. | There is no way to absorb this delay and considering priority of reports, these have to be developed before Go-live. Thus, we need to develop these reports in SIT. | FALSE | High | None | Schedule | To be assessed once requirements are available | To be assessed once requirements are available | Yes. Specs to be done before SIT. But build to be done during SIT. Expected build completion on 20-June | None |  |  | 2020-02-24 | 24/2/20 - Endorsed & Approved. Fin / Proc Functional Team & Jennifer Chemay to provide Reporting Inventory by 10-Mar. Resourcing to be done till 23-Mar to commence Specs Collection. | Phase 2 | Build | 2020-02-17 | Workstream
55 | Budget Check enabled for Projects | Projects | SIT2 | 12/06/2020 | Rochit | New extract (Map and Build) Project Budget CR needs be addressed prior to this Step1 : Address CR#72 (Completed) Step2: Adresss CR#66. Template testing in progress Step3: Include new Bidget check extract after project budget is loaded |  | Finance |  | Budgeting & Planning | Natalia Hawkins | Will Footner | Scope | Other | Adaptive Insights | Closed | Current go-live of Adaptive Insights (Planning & Forecasting solution) is now April 2021 - in alignment with HR/FIN . From go-live (Nov 2020), Hyperion (AU & VN) will no longer be viable – spread sheets / manual processes are suggested transition state. | RMIT (AU & VN) would be without a suitable Planning & Forecasting solution for 9+ months. This would provide earlier visibility of Planning & Forecasting over new structure. RMIT & Deloitte have planned different resources for this delivery. | FALSE | Medium |  |  |  |  | Yes | No |  |  | 2020-02-24 | Socialise PCG pack and receieve feedback. | Phase 3 - Adaptive Insights | Architect/Design | 2020-02-18 | PCG |  | Has been included as part of overall re-planning exercise and is now in alignment with HR/FIN go-live in April 20221
57 | Secondment will be using add additional job business process(Not Job change) | HCM Core | SIT2 | 10/07/2020 | Ken | Tri sent across and email to HR functional team for design/ requirement related information Requires configuration changes. Dependant on completion on HR team's activity for this CR | Data changes in PWC payroll system as a consequence of Workday implementation needs to be identified | Payroll |  |  | Maria Camillo | Matthew Bailey | Scope | Other | Workday | New | De-scope implementation of ADP Payroll for Spain and associated automated Workday integrations. This has been endorsed by PCG on 25 Feb 2020. | Build of integrations and business processes to support transition of Spain payroll to ADP is costly, complex and ADP solution leaves gaps in payroll management for some employees in Europe. PWC are incumbent payroll provider in Spain. | FALSE | High | No automated integrations required, however employee and financial data will need to be replicated between the PWC payroll system and Workday | Consolidated payroll reporting requirement needs to be investigated | Process for business continuity with PWC payroll solution after Workday go-live needs to be defined | [6 empty] | Impact assessment by all teams to be provided. ADP needs to be engaged for providing a contract change request | Phase 2 | SIT | 2020-03-04 16:14 | PCG
58 | Report for VNM Dependents | Reporting | NA |  |  |  | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | La Verne Legaspi |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | No data conversion relevant configuration objects | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No impact | No impact | No impact | No impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-11 | Workstream
59 | Additional compensation reporting in the Compensation tab on the People dashboard | Compensation | NA |  |  |  | No impact | Finance | La Verne Legaspi |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | 5 BPs changed incl.: budget amendment, check budget (fin.), plan event, position budget event, position budget group | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. | No impact | No impact | No impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-11 | Workstream
61 | Gift IDs in Name | Revenue (incl. gifts) & Customers | SIT1 | 24/05/2020 |  |  | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | La Verne Legaspi |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Changes to data conversion relevant configuration objects incl.: Fiscal schedule, fiscal years, ledger types, currency rate types, journal sources | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No impact | No impact | No impact | No impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-11 | Workstream
62 | New Invoice Type for VNM Student | Revenue (incl. gifts) & Customers | SIT2 | 12/06/2020 | Rochit | Mapping changes required. | No impact | Finance | La Verne Legaspi |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | 5 BPs changed incl.: Accounting adjustment event (default definition & cost center correction), accounting journal event (default definition & cost center), period close | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. | No impact | No impact | No impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-11 | Workstream
63 | Additional data load extract - SAMS | Finance | SIT1 | 5/06/2020 | Rochit | Defects raised and working through | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | Ben Matters |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Changes to data conversion relevant configuration objects incl.: transaction tax status, tax applicability | P2 Workday functional design changes |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No Impact |  | No Impact | No Impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
66 | Additional Data Load - Project Budget WOL (Whole of Life) | Projects | SIT2 | 12/06/2020 | Rochit | New extract (Map and Build) Project Budget CR needs be addressed prior to this Step1 : Address CR#72 (Completed) Step2: Adresss CR#66. Template testing in progress. Build 2 new extracts Step3: Include new Bidget check extract after project budget is loaded | No Impact | Finance | Ben Matters |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed |  | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. |  | No Impact | No Impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. |  | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12
67 | Additional Data Load - Schemes conversion | Projects | SIT2 | 12/06/2020 | Rochit/ Simon | 5 additonal extracts with Manual excel data Mapping complete: 70% Dependancy on functional team to update Manual Extract template. Complete Mapping based on Manual data Build ETL and Load | No impact | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | 7 BPs changed incl.: Customer Contract Amendment Event, Customer Contract Event, Customer Event, Customer Invoice Email Event, Customer Invoice Event, Customer Refund Event, Customer Statement Event | P2 Workday Functional Design Updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. | Requires updated test scripts | No impact | No impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
69 | Removal of Time Off Codes | Absence and Time | SIT2 | 05/06/2020 | Kathleen | New configuration workbook required to anusre all Time off Codes are removed/ Replaced accordingly. | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | Ben Matters |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Changes to data conversion relevant configuration objects incl.: | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No Impact |  | No Impact | No Impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
72 | Project Budgets - Add Template for Project Level - Data Conversion | Projects | SIT2 | 12/06/2020 | Rochit | New extract (Map and Build) Project Budget CR needs be addressed prior to this Step1 : Address CR#72 (Completed) Step2: Adresss CR#66. Template testing in progress. Build 2 new extracts Step3: Include new Bidget check extract after project budget is loaded | No Impact | Finance | Ben Matters |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | BPs changed incl.: expense report event, spend authorisation | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. | No Impact | No Impact | No Impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
73 | Reconciliation file between ADP and WD | Compensation | NA |  |  |  | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Changes to data conversion relevant configuration objects incl.: project hierarchies, project tasks, project template, project plan template, resource plan template | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No impact |  | No impact | No impact | No impact |  | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
79 | Worktag Usage Change for Assets | Assets | NA |  |  |  | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Changes to data conversion relevant configuration objects incl.: Customer Category, Customer Group, Invoice Type, Release Levels | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No impact |  | No impact | No impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
80 | Lease Setting change for Spend Cat - SC_10005 Leasehold Improvement | Expenses | SIT1 | 24/05/2020 |  |  | No impact | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | 6 BPs changed incl.: Convert opportunity project to project, Create project, Edit project, Project resource plan line, Project transaction adjustment event, Request worker | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. |  | No Impact | No Impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
81 | ADP - Change supplier invoice template to separate the Tax Code and Tax Applicability | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Changes to data conversion relevant configuration objects incl.: release levels | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No Impact |  | No Impact | No Impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
82 | Sale of Asset - Change Account Posting Rule | Revenue (incl. gifts) & Customers | SIT2 |  | Rochit | To check with Rochit | No Impact | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | 2 BPs changed incl.: Donor contribution event, Gift event | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. |  | No Impact | No Impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
83 | Revenue Categories - Tax Mapping | Revenue (incl. gifts) & Customers | SIT2 |  |  | Simon to check with Ryan | No impact | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | 5 BPs changed incl.: Asset Assign Accounting Event, Asset Cost Adjustment Event, Asset Disposal Event, Asset Impairment Event, Asset Issue Event | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. |  | No impact | No impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
84 | Addresses of Payee and Payees' Financial Institutions required for Western Union Integration | Settlements | SIT2 | 03/07/2020 | Adeelah | Data Cleasning required. Step1: Mapping Step 2: Build & Load | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | Aimee Mensink |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Changes to data conversion relevant configuration objects incl.: Supplier Groups, Units of Measure | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No impact |  | No impact | No impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
85 | Migrate completion of compliance course - Course code 9148 | Talent | SIT1 | 24/05/2020 | Kathleen |  | No impact | Finance | Aimee Mensink |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | 21 BPs changed incl.: Ad Hoc Paym, Adv Ship Notice, Catalog Load, Change Order, Create Contract Schedule, Requisition, PO, RFQ & Response, Award, Supplier Contract BPs, Supplier Request and Creation, Supplier Classification, Supplier Invoice BPs | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. |  | No impact | No impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-12 | Workstream
89 | Updates to Banking Config WB -AHBT Templates and Bank Accounts Tab | Banking | NA |  |  |  | This data is currently stored in excel spreadsheets and the current HRMS in VN. Discussed with the data team and this will be part of the data migration effort which is small. Please see attachments | HR | Chi Nguyen | Benefits | Renee Teranen | Michael Currie | Scope | Workday |  | Approved | There is a requirement from VNM to capture passport number for foreign dependents in Vietnam | The passport number (or ID number) of dependents is required to support the benefits module. In particular to be able to pass on any benefits to employee dependents. This information is sent across to insurance companies which require this information | FALSE | Medium | None | An existing report (RMIT Visa Compliance) will be used to report on passport information for employees. There will be minimal changes made to this report to accommodate this change i.e. additional ID. Please see attachments | None | None | None | None |  |  | 2020-03-23 | Configuration for SIT | Phase 2 | SIT | 2020-03-12 | Workstream |  | Felix: Have communicated with data team about this CR. They are aware and aligned.
90 | Budget Amendment Type - Position Budget | FDM, Budgets | NA |  |  |  |  | CLM |  | Source to Contract | Michelle Paez-Kirkland | Brad West | Scope | iCertis |  | In Analysis |  |  | FALSE | High | [7 empty] | 2020-03-27 |  |  | Phase 3 - Advanced HR | Go-Live | 2020-03-13 | PCG
92 | Request to data convert employee Expense Account election as part of the Workday Payment Election in HCM | HCM Core | SIT2 | 05/06/2020 | Tri Lam | Check with HR functional team on the requirement and verify if Hoover scripts require changes | These codes don't exist in current system so no impact to Data. | HR | Chi Thi Lien Nguyen | Payroll | Renee Teranen | Matthew Bailey | Scope | Workday | ADP | Approved | VNM have requested 15 new Time Entry codes. | Greater accuracy when recording hours worked. 1 of the time entry codes ensures compliance with VN Labour Law. Each time entry code will hold an associated ratio which ADP will interpret and generate the correct number of hours payment. | TRUE (must explain in Change Control justification) | High | New time entry codes to be mapped. Integration impact is 2 hours to map in the integration and unit test. | No impact, however calling out all reports will be based on hours entered, not the resulting ratio payment. | Managed via Change / Training comm's. | Nil | Nil |  | Additional scenarios to be tested | 2020-03-16 | 2020-03-23 | Workday Time and Absence workbook has been updated with new Time Entry codes. | Phase 2 | SIT | 2020-03-13 | Workstream |  | ML 19/03:- Confirmed with Wendy that all required impact assessments have been made and this item is ready for approval
93 | Two additional allowance plans | Compensation | NA |  |  |  | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance |  |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Changes to data conversion relevant configuration objects incl.: Bank Accounts | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No impact | Payment Types updates in X-functional workbook. | No Impact | No Impact | No impact |  | 2020-03-20 |  | Phase 2 | SIT | 2020-03-13 | Workstream
95 | CLM Integration IR09 - INT442 Customer Master | Contracts | NA |  |  |  | No Impact | Finance |  |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | 5 BPs changed incl.: Ad hoc bank transaction, bank statement, print checks, remittance release, settlement run | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | Changes need to be reflected in Training and Communication materials. Assignment of sec roles to positions for SIT will cover the changes to sec roles in BPs. No changes to sizing. | No Impact | No Impact | No Impact | Testing scenarios to be updated. Details on the changes are documented in the P2 BP Workbooks. |  | 2020-03-20 |  | Phase 2 | SIT | 2020-03-13 | Workstream
96 | Position Budget conversion | FDM, Budgets | SIT2 | 12/06/2020 | Rochit | New extract. To check with Rochit for SIT2 Mapping in progress. Build to commence on 5/06 | Mapping to be updated. Details on the changes are documented in the P2 Config Workbooks | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | No changes | P2 Workday functional design updates |  | Medium | No expected impacts, design during integrations design session should reflect the P2 decisions | WD Reporting team is across changes made and will reflect changes in the reports. | No impact |  | No impact | No impact | No impact | 2020-03-20 | 2020-03-20 |  | Phase 2 | SIT | 2020-03-16 | Workstream
97 | Intercompany Accounting Journals - Custom Validation | Fin Accounting | NA |  |  |  | None | Payroll |  |  | Maria Camillo | Chaun Kam | Integration | Other | Workday | New | Needing a CR to change the G2 integration to allow for creation of New Cost Centers from WDinto ADP |  | FALSE | Low | Needs CR to create the G2 integration appropriately to allow new cost centers | None | None |  |  | None |  |  |  |  | Phase 2 | Prototype 2 | 2020-03-16
98 | Casual LSL | Absence and Time | NA |  |  |  | Data mapping, ETL Build, Hoover Build, Validation Report Build will be required. Potential additional data sources not in SIT need to be added. Project Budgets are a prerequisite to this data load, these are not currently in scope pending change request. | Finance | Omer Bilal | Data | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Pending Approval | Budget checks required to be enabled for all project budgets that have been loaded. | P2 Workday functional design updates |  | High | No expected impacts | No Impact | No Impact | No Impact | No Impact | No Impact |  |  | 2020-03-24 | Data team to review feasibility & requirements | Phase 2 |  | 2020-03-17 | Workstream |  | '- data mapping already done - load pushed for June 5 - agreed to have it reflected in this load
101 | Business Asset Accountant Security | Assets | NA |  |  |  | Not applicable | Procurement Ops | Stephen Coles |  | Jen Kyle | Brad West | Scope | Workday |  | Closed | RMIT will not be using the RFQ functionality within Workday and instead allowing users to attach quotes and create requisitions without using the RFQ functionality. | P2 design change | FALSE | High | Not applicable | Reports to be reassessed to meet design change | to be confirmed | Change impact assessment, test cases | 1 week delay in sign off of P2 |  | Current test cases will be impacted. Assessment to be completed by 3rd April | 2020-03-27 | 2020-03-30 | Endorsed and Approved - (approved in Change Impact Asses. Using RFQ manual attach for RFQ). Impact assessment on configuration, business processes, test cases, CIA, reporting | Phase 3 - Advanced HR |  | 2020-03-20 | Sponsor | PMC 668553 | This will result in three business processes being de-scoped along with a potential integration for RFQ BIRT form. Request for Quote Event Request for Quote Award Event Request for Quote Response Event
103 | HR Go Live Reports | Reporting | NA |  |  |  | This needs to be now converted as additional job and not as job change. We did meet up with the team to walk them through the changes, for SIT phase secondment conversion was not in scope so this is not immediate impact but covered in UAT. | HR | Snehal Kabra |  | Renee Teranen | Michael Currie | Process | Workday | ADP | Approved | Secondments will be using add additional job business process (Not Job change) | Original design for staff on secondment was using change process. However post P2 workshops options were presented to Business and on evaluation the result is a decision to use add additional job business process to cater for this. | FALSE | High | An email is sent to all respective leads and teams to socialise this change and analyse the impact. James and Matthew have had further clarifications with me on emails to confirm the process and have indicated no real impacts. | Reporting team is communicated to and a new reporting requirement is also added, not just for this change but for overall multiple position. | Services team have been informed that additional jobs (secondments) will be going via the talent acquisition team as a job requisition. Michelle Poulton is accross this, refer to attachment. | Payroll was in the room where this process was presented and decided upon, no impacts identified (Maria and Cara)Time and Absence- as a new leave type is required to be added, they are notified and will be further communicated once CR is approved. | Ready for UAT | None | We had given heads up in our last review. New test scenarios added. Neethu and Jason are across. Anne and Amey were part of the walk through on the process change.SIT 2nd round if it goes ahead will enable this testing for secondment scenarios. | 2020-03-30 | 2020-04-15 | 15/3 - Endorsed & Approved. Finance and Date approved. 6/3 - Eric, Natalia and Renee to discuss off-line. Upon approval, design for Leave Type (secondment) will be required by the Absence team and the updates will be made to business processes | Phase 2 | SIT | 2020-03-23 | Workstream |  | 06/04: reviewed in CR meeting, review in further detail. High risk adding conversion in for the first time in UAT. Eric, Natalia, Renee to report back.Caught up with Natalia(reports will be provided) & Eric(Data conversion & SIT plan discussed).
104 | New Worktag - Program to be included in ADP Integration | Finance | SIT2 | 19/06/2020 | Tri Lam | Tri to review and advice further steps | No | HR | Chi Nguyen | Benefits | Eric Hoffman |  | Reporting | Workday |  | Approved | As a result of VN P2 workshop, the HR VN Team requested to have the medical insurance report built to support internal management and external submission. | All details mentioned in the report template are stored on Workday. | FALSE | Medium | No | New report design | No | No | No | Not sure | Need to be test in SIT |  |  | 6/4 - Endorsed and Approved. Reporting Team to build a report based on the report template provided by VN in this CR. | Phase 2 | SIT | 2020-03-23 | Workstream |  | This report will be used for both 1/ Dependents under Benefits and 2/ Dependents under Tax Relief
105 | RMIT Training FS EA | Compensation / Absence and Time | SIT2 | 26/06/2020 | Kathleen | Kathleen to understand the impact of changes and request for configuration changes in workday Check-in on 08/06/2020 | Just the reporting impact. All data from Workday | HR | Tom Koola | Reporting | Renee Teranen | Michael Currie | Reporting | Workday |  | Approved | Adding 3 new reports to the Compensation tab on the People dashboard | More value add reports that will support managers at go-live to manage compensation | FALSE | Medium | No integration impacts | Primarily reporting | The reports can be used by services team to support managers in the transition to WD to manage compensation of their direct reports | NA |  | Potentially - Rahul Padhiar owns this CR from the business | Just unit testing |  | 2020-04-06 | 6/4 - Endorsed and Approved. (Approval that this is being added to backlog). Effort estimation for build and time-frames to be decided | Phase 2 | UAT | 2020-03-24 | Workstream |  | Rahul will own and manage this CR with the reporting team - with input from the Compensation team
106 | Manual Integration requirements - Finance | Reporting | NA |  |  |  | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | Feedback from DA review to amend Business Processes to prevent any issues with master data. Customer Summary Change, Customer Credit Change require same validations as Customer event | Master Data Governance | FALSE | Low | N/A | N/A | N/A | N/A | N/A | N/A | Added Condition Rules on BP require testing |  | 2020-03-30 | 30/3 - Endorsed and Approved. Not impacting other streams. Configure SIT tenant, Update Workbooks | Phase 2 | SIT | 2020-03-25 | Workstream
107 | Creation of custom field to capturing Employee's Indigenous Status (personal information field) | HCM Core | SIT2 | 12/06/2020 | Kathleen | The data is not captured in legacy system. Data conversion is not feasible Kathleen to email Snehal and get further feedback | Change to ETL logic (Simple Change) | Finance | Tracey Brown |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Approved | Please tick box to include Gift ID in name |  | FALSE | Low | none | none | none | none | none | none | none |  | 2020-05-18 | 18/5 - Endorsed and approved. Changes made to existing configurations post P2. | Phase 2 |  | 2020-03-25 | Workstream |  | Data has been mapped/ loaded in WD for SIT
109 | Tax Status for Customer, Supplier and Company | Tax | SIT1 | 24/05/2020 |  |  | Data can now map to the new value | Finance | Tracey Brown |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Approved | New Invoice Type 'Student' to easily identify and segregrate this Customer group by invoice | [11 empty] | 2020-05-18 | 18/5 - Endorsed and approved. Changes made to existing configurations post P2. |  |  | 2020-03-25 | Workstream |  | data has been mapped/ extract has been generated – data load into WD is still pending with Simon
110 | Tax Exports Customer Validation for Customer | Tax | NA |  |  |  | Data will need to load the reclassification journal | Finance | Tracey Brown |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Approved | An additional data load for SAMS needs to be done in SIT to do a reclassification by worktags. | Crictical to test SAMS revenue mapping logic |  | High | [8 empty] | 2020-05-18 | 18/5 - Endorsed and approved. Changes made to existing configurations post P2. Provide SAMS mapping to Data. Provide SAMS actuals YTD Feb 20 | Phase 2 |  | 2020-03-25 | Workstream |  | SAMS: agreed on data source & proof of concept – data mapping is in progress, target for early May data load
111 | Work Schedule - ID Ref Change to identify Country | Absence and Time | SIT2 | 12/06/2020 | Ruhi/ Ken | Dependant on configuration change. | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Closed | Prevent the Initiator from approving any Refunds (SoD) | Security roles currently in place to prevent this from happening. This is a secondary measure to ensure it is impossible if a person was assigned both security groups to approve their own request | FALSE | Medium | N/A | N/A | N/A | N/A | N/A | N/A | Requires testing with somone who has Customer Refund Specialist and AP,AR Approver to create a refund |  | 2020-03-30 | 30/3 - Approved & Endorsed. Not impacting other streams. Configure BP and update Workbook | Phase 2 | SIT | 2020-03-25 | Workstream
112 | Adjustment to Spain Leave Calculations | Absence and Time | SIT2 | 12/06/2020 | Ken | Ken to request for data. | N/A | Finance | Ryan Auteri | Integration | Natalia Hawkins | Aneta Wielgus | Integration | Workday | UNIONE | Closed | Require a Journal Source for the UNIONE GL Feed Integration | Principle has been set that each GL Feed is to have its own Journal Source - Consistency | FALSE | Low | Value required for Integration Mapping | N/A | N/A | N/A | N/A | N/A |  |  | 2020-03-30 | 30/3 - Endorsed and Approved. Not impact on other streams. Populate workbook and configure | Phase 2 | SIT | 2020-03-26
113 | Bank Rec & First Notice Rule Changes | Finance | NA |  |  |  | Requirement for potential new ETL process for SIT and subsequent phases. | Finance | Omer Bilal | Data | Natalia Hawkins | Aneta Wielgus | Data | Workday | PPM | Approved | Project Budget WOL (Whole of Life) not yet included in the Data loads. Request to review and update SIT data load to include relevant data | Required to load Whole of Life budget for each Project | FALSE | Medium | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2020-05-18 | 18/5 - Endorsed and approved. SIT2. For data conversion, we would need functional to confirm: - Data source - Data detail component to be converted into WD - Any migration/mapping logic from source to WD Confirm how the data loads will be done and when to be tested, required to be done before go-live. | Phase 2 | SIT2 | 2020-03-29 | Workstream
114 | Bank Account Configuration - account usages, allowed payment types, integrations | Finance | NA |  |  |  | Not in P2 load and need assessment on how to do data conversion for SIT | Finance | Omer Bilal | Data | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Pending Approval | New data load required for SIT to cater for Schemes | No in initial data loads but required within Workday | FALSE | High | N/A | N/A | N/A | N/A | N/A | N/A |  | 2020-04-03 | 2020-04-03 | For data conversion, we would need functional to confirm: - Data source - Data detail component to be converted into WD - Any migration/mapping logic from source to WD - Scheme Budget Template to be created | Phase 2 |  | 2020-03-29 | Workstream
115 | Fixed casual rate for a casual academic | Compensation | SIT2 | 19/06/2020 | Kathleen | Mapping and ETL change only | Current to new spend category mapping and expense item | Procurement Ops | Lindy Witton |  | Jen Kyle | Brad West | Scope | Workday |  | Closed | Changes resulting P2 - 16 do not impact Finance, others due to documentation issues, Vietnam, Finance and expense mapping. | P2 Design Change | FALSE | High | Not applicable | Have been updated | No impact | Finance impacts in change log | None |  | Test Cases not impacted | 2020-04-15 | 2020-04-15 | 15/4 - Endorsed and Approved. | Phase 3 - Advanced HR |  | 2020-03-30 | Program | 670731 | 15/4 - Endorsed and Approved. Discussed and agreedwith Natalia and Eric during the week. 06/04 - CR reviewed: Review offline this week, Eric, Lindy, Natalia. Chgs req'd to be reviewed Data/FIN. Target to build into SIT post data config (~3 wks).
116 | New Project Role - Project Creator | Projects | NA |  |  |  | EH:- Approved for SIT 2 with minor update to cross walk required | HR | Wendy Draper |  | Renee Teranen | Michael Currie | Configuration | Workday | ADP | Pending Approval | Removal of Time Off codes due to new LSL design | We no longer need to track LWOP–Sick/Carers Leave separately. Changes will be: 1.Removal of the LWOP - Carers Leave Time Off 2.Rename LWOP – Sick to LWOP and enable the time off reasons of Sick Leave with Cert, Sick Leave without Cert. & Carers Leave. | FALSE | Medium | CK:- Minimal work with a simple update to mapping document | The following reports may be impacted: •RMIT Workers on Half Pay and LWOP-Time Off •RMIT Unscheduled Absenteeism Matrix Report • RMIT Workers on Extended Sick Leave RK:- We see the effort to be minimal. | N/A | WD:- Leave without pay codes so no impact to finance mapping | N/A | N/A | Change to SIT data mapping testing performed by Deloitte. Confirm with Michael and Suet | 2020-05-25 |  |  | Phase 2 | SIT2 | 2020-03-31 | Workstream |  | MC:- This change has already been implemented in ADP
117 | Capex Settlement to WIP accounts - Replace Project Group with Optional Project Hierarchy | Projects | SIT2 | 12/06/2020 | Rochit | Functional team already provided rule. Mapping to be updated for Project template | To be catered for in data conversion data load | Procurement Ops | Lindy Witton | CLM (Expense Contracts) | Jen Kyle | Brad West | Process | Workday | icertis | Closed | An additional contract type is required in Workday for the different approvals required at the requisition stage. A new icertis contract purpose required to drive workflow in workday based on workday contract type. | P2 Playback design change | FALSE | High | No additional Integrations required. Will need to send different contract types from Icertis | Not applicable | Process and testing will be impacted (minimal changes required to accommodate variations to existing scenarios) | Change impact assessment, test cases, icertis Workday contract type drop down | No impact | Nil | Current test cases will be impacted. Assessment to be completed by 3rd April | 2020-04-09 | 2020-04-20 | Update configuration workbooks and build | Phase 3 - Advanced HR |  | 2020-03-31 | Program | 670736 | Where contract type is Non MSA - Cost Centre Approval and DOA is not required (in Icertis). Where contract type is MSA, both Cost Centre and DOA are required as are agreed to centrally and will require local review and approval prior to comitment.
118 | Tax Defaulting for Intercompany Transactions (AUS - VNM) update | Tax | SIT2 | 12/06/2020 | Simon | Changing a value in file | Correct location mapping | Payroll |  |  | Maria Camillo | Matthew Bailey | Integration | Workday | ADP | Cancelled | Adding locations in Workday to enable payroll and workcover tax | Statutory compliance - currently manual efforts | TRUE (must explain in Change Control justification) | Low | Yes - Integration of correct locations from Archibus -> WD -> ADP (james to advise) .. minimum impact from Chaun | No impact as advised by Rafay | No impact | HR Impact - Core, impact on build. Comp, no impact as advised by Felix. Talent, No impact as advised by Chai. |  | TBA |  | 2020-04-27 |  | Assess cost and timeliness of change to enable change decision | Phase 2 | SIT | 2020-03-31 | Workstream |  | Closing CR due to business requirements
120 | RMIT Spain - Supplier Payment File to La Caixa Bank | Finance | NA |  |  |  | Enables Data Conversion | Finance | Ryan Auteri | Budgets | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Approved | Enable Project Budget to be at Project Level, Rather than just Task Level | Data Conversion process is to load budgets at Project not task level | FALSE | High | N/A | N/A | N/A | N/A | N/A | N/A |  | 2020-04-10 | 2020-04-06 | 6/4 - Endorsed and Approved. Update Workbook, Configure tenant | Phase 2 | SIT | 2020-04-02
121 | VN Benefit - Update eligibility of dependents | Compensation | SIT1 |  |  |  | No impacts to data | HR | Tom Koola | Payroll | Renee Teranen | Michael Currie | Reporting | Workday | ADP | Approved | Audit report for values in ADP and WD | Governance to ensure data integrity in both systems | FALSE | High | No impacts to integration | Primary impact to build report - Power BI report | No impacts to process and services | Payroll will need to provide input into the report | No impacts to schedule | No impacts to cost | to be included in testing | 2020-06-30 | 2020-04-20 | Build report to cover all common fields between ADP and WD in Power BI. | Phase 2 | SIT | 2020-04-02 | Workstream |  | TK - This report will be ran at predetermined intervals to ensure that the data in WD matches ADP. I have added this to the Reporting Backlog. Dhania and Jyotsna are across this request. Approved for backlog
122 | New Role - Project Portfolio Manager | Projects | NA |  |  |  | The data stream has been mapping Suppliers to both Supplier Groups in order to minimise the impact. Suppliers will be reloaded with the signed off groups prior to UAT. | Procurement Ops | Lindy Witton | Finance | Jen Kyle | Aneta Wielgus | Data | Workday |  | Closed |  | Supplier Groups – Procurement P2 changes to Supplier Groups to be made available in time for SIT. The Supplier Group changes are: - No Changes = 9 - Updates to Supplier Group Name = 61 - Confirming those to be deleted = 102 - New Supplier Groups = 23 | FALSE | High | Not applicable | There will be workarounds in SIT to test reporting, but no impact to the development of reports. | Nil | Impact to Finance Stream as Users of the Supplier Groups and impact to the Data Stream as they have had to map to both the pre and post signed off Groups. | Nil | Nil | Agreed for SIT- if config has not been updated, old supplier groups to be used | 2020-04-06 | 2020-04-06 | 6/4 - Endorsed and Approved. Update Workday and assign suppliers | Phase 2 |  | 2020-04-02 | Program | 672195
123 | System warning/notification for inactive suppliers | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | Reduced Data Load | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | SIT signoff moved this field into the Customer Group, but we didn't remove the Field from the Custom Object Tab | Alignment of Config Workbook | FALSE | Low | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2020-04-06 | 6/4 - Endorsed and Approved. |  |  | 2020-04-05
124 | AHBT Templates - Vietnam and Corporate Credit Cards; CC 1st notice rules | Banking & Settlements | NA |  |  |  | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Integration | Workday |  | Closed | TS24 fields are required to be added to the Customer Invoice Object so that data can be sent to - receive from TS24 for VNM Tax Invoices | Knew it was required - requirements came from integration meetings after SIT signoff - Required for TS24 reporting - Legislative | TRUE (must explain in Change Control justification) | High | Request came from Integrations | N/A | N/A | N/A | N/A | N/A | will need to be included |  | 2020-04-06 | 6/4 - Endorsed and Approved |  |  | 2020-04-05
126 | Payment Release BP configuration updated | Banking & Settlements | NA |  |  |  | N/A - Nothing mapped to this revenue category | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Remove Revenue Category - Bad Debt Write Off | Spend Category of Bad Debt Write Off exists - as it is mapped to an expense account | FALSE | Low | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2020-04-06 | 6/4 - Endorsed and Approved. Update Config Workbook |  |  | 2020-04-05
128 | Custom validation to warn user to select ‘catalogue’ when creating a catalogue contract, | Procurement (Sup Contract, RFQs) | NA |  |  |  | N/A - No Mapping Changes - Just Description Change | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | 5300 incorrectly named "Interest Expense" instead of "Intercompany Expense" - 5200 is correctly named "Interest Expense" | Incorrect Naming | FALSE | Low | N/A - No Mapping Changes - Just Description Change | N/A - No Mapping Changes - Just Description Change | N/A - No Mapping Changes - Just Description Change | N/A - No Mapping Changes - Just Description Change | N/A | N/A | N/A |  | 2020-04-15 | 15/4 - Endorsed and Approved. No cross functional impacts. |  |  | 2020-04-07
129 | Instrument Free entitlements | Absence and Time |  |  |  |  | Preventing data load (Temporary change already made to allow data to continue) | Data | Hunter Pool | Projects | Alex Dieng | Aneta Wielgus | Data | Workday |  | Pending Approval | Project Task is a worktag on Assets. Assets created through capital projects are not generating a Project Task on the asset once it's registered. We're suggesting changing the worktag on assets from Project Task to Project. | Assist with data loads and provides more accurate data from project to asset | FALSE | Medium |  | N/A | N/A | N/A | N/A | N/A |  |  | 2020-05-18 | Testing on reporting impacts to be conducted by the finance functional team | Phase 2 | SIT | 2020-05-14 | Workstream
131 | Vietnam Student Customer Management | Finance | NA |  |  |  | This change is resulted from data load defect request. [JIRA] (PPDS-6457) Unmasked - Vietnam Asset, non leased assets with lease spend category. | Finance | Truc Luu | Data | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Approved | this change is resulted from data load defect request, i.e. the lease setting for SC_10005 Leasehold Improvement need to be unticked in order to facilitate assets data load. | This is currently holding off assets data load for both AU & VN. | FALSE | High | NA | NA | NA | NA | NA | NA |  | 2020-04-08 | 2020-04-08 | Pre approval sought (SC_10005 Leasehold Improvement need to be unticked ) to continue on with asset data load | Phase 2 | SIT | 2020-04-08 | Workstream |  | [BK 9th Apr] Approved off-line by Eric, Jen & Natalia - details in attached
133 | Retained Earnings - Allowing Gift Worktag | Finance | NA |  |  | Need to check if a new CR comes through to bring opening balance for Gifts | NA | Payroll | Andrew Semmens | Finance | Maria Camillo | Matthew Bailey | Integration | Other | Workday | In Analysis | change the supplier invoice template to separate the Tax Code and Tax Applicability | makes us easily identify the fields & corresponding values | FALSE | Medium | Yes - Change to existing ADP Supplier Template | NA | NA |  | NA | NA |  | 2020-04-24 | 2020-04-17 | ADP to review details & requirements. [BK 09-Apr] Quote from ADP received. Approved by Michael V and CR with ADP approved by Maria. Integrations team to review / confirm change. | Phase 2 | SIT | 2020-04-08 | Program |  | Attachment has suggested layout - current and proposed format. [BK 09-Apr] Quote from ADP received. Approved by Michael V and CR with ADP approved by Maria.
134 | DA Outcome - Amend Minimum Threshold for Customer Write-Offs | Finance | NA |  |  |  | Update to Data Mapping File - Change Revenue Category - Sale of Asset to Gain on Sale of Asset | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Approved | Change the Account Posting Rule of Sale of Asset to hit Trade Receivables. Required to perform correct accounting across the Customer Invoice (Sale) and the asset disposal | Must be performed for correct recognition of accounting - Currently No Link between Customer Invoice and Asset Disposal | TRUE (must explain in Change Control justification) | High | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2020-05-18 | 18/5 - Endorsed and Approved. Update Config Workbook, Update Tenant, Vote on Brainstorm - https://community.workday.com/brainstorms/509806 | Phase 2 |  | 2020-04-13
135 | Update to have asset usage on Campus location type to enable searching when issusing/transferring an asset | Finance | SIT2 | 12/06/2020 | Simon | Mapping change in Campus Location extract | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | In Analysis | Updates to GST Mapping / Alignment of Naming | Update to alignment |  | Low | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Phase 2 | SIT | 2020-04-14
136 | iCertis Descope - Customer Contract BP Documentation | Finance | NA |  |  |  | Supplier address components required for the field are: Street Address, City, State, Postcode. Must appear in this fixed format for integration to operate correctly. | Finance |  | Customer & Supplier | Natalia Hawkins | Aneta Wielgus | Integration | Workday | Western Union | Approved | Change to Supplier, Customer, Ad Hoc Payee bank account information to store the addresses of Payees' financial institutions in the field "bank instructions" and enforce payee address to be captured | Requirement from Western Union to include this data in the payment file integration to them. Currently provide this data from SAP | FALSE | Medium | Additional transformation needed for integration to split contents of Bank Instructions Field into position required by WU. | Impact assessment done on 1-May. No Impact. | Custom validation to be created to ensure this is mandatory field for all Payees that have Western Union as an allowed payment type. Applies to Customers, Suppliers, and Ad Hoc Payees | [5 empty] | 2020-05-04 | 4/5 - Endorsed and Approved. 27/4 - Remains pending approval. Aneta to discuss with Data and Finance. | Phase 2 | SIT | 2020-04-15 |  |  | Changes have been discussed and verified by Tracey Brown (customer lead), Andrew Semmens (Supplier Lead). Adeelah (Data), Aashish and Winston (Integrations team)
140 | Review Payment Acknowledgement BP - Initiating security changed | Banking & Settlements | NA |  |  |  | Yes there will be data impacts as ALL compliance course data (not only 2 years) for employees will need to be migrated from SAP into WD | HR | Dharitri Desai |  | Renee Teranen | Michael Currie | Data | Workday | Bridge and SAP | Approved | Migration of completions of course 9148 from SAP into Workday Talent Training irrespective of completion date for all active staff | Course 9148 is a compliance course to be completed only once on joining organisation. Only for the course 9148 completions will have to be migrated irrespective of when the course was completed. | TRUE (must explain in Change Control justification) | High | No integration impacts | "Impact type: Change to existing report # of reports impacted: 1 Name of reports: Education Compliance" | No process and services impacts | No cross functional impacts | No schedule impacts | No cost impacts | No testing impacts |  | 2020-04-20 | Get approval in next CR approval meeting i.e. Mon 20/04 | Phase 2 | SIT | 2020-04-15 | Workstream |  | Meeting was held with business and data stream on Thu 09/04 to discuss and no major issues raised for this CR in getting approved
141 | Update to Ad Hoc Bank Transaction BP | Banking & Settlements | NA |  |  |  | Contracts / Billing Schedule / Revenue recognition schedule to be loaded into workday Eric / Simon have agreed actions and process to move to SIT is occuring | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Scope | Workday | iCertis | Closed | Workday will store the Approved Contract, Billing Schedule, Revenue Recognition schedule. Invoicing will occur out of Workday | Agreement from CLM and Finance Leads | FALSE | High | Integration impacts captured as part of iCertis Work | Some reports are already scoped | Process impacts | Yes | N/A | N/A | E2E test scripts to be amended |  |  | Build Tenant Per Change Request - Build Test Scripts - Data Conversion | Phase 2 | SIT | 2020-04-15 | Workstream |  | Will be created in workday. The data may come in separate way, once milestone is fulfilled the invoice will be created and issued from workday. Changes can be made prior to SIT. Data ability to meet timeframes? Delivery dates TBC
142 | Ad Hoc Payments - mandate payee email address in 'Alternate Name' field to facilitate AHP remittance advice | Settlements | NA |  |  |  | Data conversion approach changing for SIT - so field required to be mapped | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Closed | Update Customer Contract Types to be the same as Purpose Field in iCertis (Previously was a different field) | Previously mapped field was too low level - this was already agreed in principle. Values have now been provided so change is raised | TRUE (must explain in Change Control justification) | Low | N/A - field mapping exercise still to be performed | N/A | N/A | N/A | N/A | N/A |  | 2020-04-20 | 2020-04-20 | Update Workbook, Build in tenant | Phase 2 | SIT | 2020-04-15 |  |  | Created in workday. The data may come in separate way, once milestone is fulfilled the invoice will be created and issued from workday. Changes can be made prior to SIT. Data ability to meet timeframes? Delivery dates TBC.
143 | Supplier Invoice Request BP to be brought into scope | P2P (R2P2R, I2P, Supplier Record) | NA |  |  | Need to check the scope | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Integration | Workday |  | Closed | New Journal Source (Standard for Integration), Spend Category and Ledger Account to be created to facilitate the labour recovery logic | Required to capture salary recovery / contingent worker charging | FALSE | Medium | Enables the integration to run - already captured in design spec | N/A | N/A | N/A | N/A | N/A | need to be covered in testing |  | 2020-04-21 | 21/4- Approved. Email of approval provided by Manish Pandy after completion of impact assessment. - Populate configuration workbook - develop integration | Phase 2 | SIT | 2020-04-16 |  |  | Pending assessment of effort from mulesoft - decision can be made via email group if low effort estimates come back (Manish to follow up).
144 | Update Deferred Revenue Posting | Finance | NA |  |  |  | Bank West is a closed bank account, added to facilitate data rec as it was still open in February | Finance | Sarah Dozortseva |  | Natalia Hawkins | Aneta Wielgus | Data | Workday | NA | Approved | Bankwest account added. Corrections to rec config (missing first notice rule sets, advanced mode). AHBT Template cost centres .Placeholders for some first notice rules as condition logic supplied in CW cannot be built. | Bank account configuration was not consistent/causing iload issues. Cost Centres provided for some templates are populating different name for the code provided to what is in the CW. Config to be reworked next week. | FALSE | Medium | N/A | NA | NA | NA | NA | NA | Correct information/config for templates and first notice rules needed for accurate testing |  |  |  | Phase 2 | SIT | 2020-04-16 | Workstream
145 | Creation of custom field to capturing Employee's Indigenous country or Indigenous Nation group (personal information field) | Human Resources |  | 12/06/2020 | Kathleen | Same as 107 | N/A | Finance | Rob Penn-Tonkin |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | New | New Budget Amendment Type - Position Budget Amendment created | Bank West is a closed bank account, added to facilitate data rec as it was still open in February | FALSE | Medium | N/A | N/A | N/A | Position budget amendment type created for HR | N/A | N/A |  |  |  | Populate config workbook and update object master tenant (RMIT5) | Phase 2 | SIT | 2020-04-17
146 | Removal of Wire Payment Type - RMIT Aust Entities & RMIT Indonesia | Settlements | SIT2 | 19/06/2020 | Adeelah | Mapping change for supplier payment types and build | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Integration | Workday |  | Closed | Company Code Values are required for all companies - enables settlement integrations to work | Consistency ¦ Settlement Integrations | FALSE | High | Integration Requirement - No Negative impact - Field is required for certain ntegrations | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 27/4 -Aneta to follow up with Data and Finance and may be off-line approval via email. Update Configuration Workbook, Update Tenants | Phase 2 | SIT | 2020-04-17 |  |  | No impacts to procurement, data. Approved
148 | Procurement Security Roles changes (Specialist Buyer role) | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | Require new expense account election in our Payment Election load file. This will mean an extra record for all employees. | HR | Ben Matters | Payment Election | Alex Dieng | Aneta Wielgus | Data | Workday |  | Approved | Request to data convert employee Expense Account election as part of the Workday Payment Election in HCM | The existing expense solution (ProMaster), does not hold employees' banking details, but are leveraging from Payroll. For all current employees we need to use their payroll primary bank account in the system as default for Expenses. | FALSE | Medium | Integration will need to ensure they will be picking this up from Workday to send to ADP. |  |  | Required by Finance. Will impact both Data and Integrations. | To be determined. | To be determined. |  |  | 2020-04-27 | 27/4 - Endorsed and Approved. Eric to analyse on data conversion impact | Phase 2 | UAT | 2020-04-20 |  |  | No data conversion impacts. Missed requirements in previous workings to get this incorporated in HR module.
149 | Provide ability for Procurement Administrator to manage Supplier Groups | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | None | HR | Tom Koola | Payroll | Renee Teranen | Michael Currie | Configuration | Workday | ADP | Approved | Two additional allowance type created as per request from the business | Business request | FALSE | Medium | Yes - Mapping for earning codes between WD and ADP | RK: Impact assessment done on 1-May. 1 Workday and 1 Cross-func report impacted (changes to these reports). | None | ADP only - new values to be created in ADP | None | Maybe at ADP end | Only impact is the visible allowance list. No other impacts to testing | 2020-05-01 | 2020-05-04 | 4/5 - Endosed and Approved. PMO decision: Will build for SIT, process CR with ADP and the GL readiness will be within SIT2. allowance can be mapped and sent across. | Phase 2 | SIT | 2020-04-20 | Workstream |  | Email communication sent to ADP; Data; Reporting; Integration and Testing. Configuration update in WD and ADP. Update Data Dictionary.
150 | Contingent workers removed from Expense Report Business Process in Workday | Expenses | NA |  |  |  | tba | HR | Wendy Draper |  | Renee Teranen | Michael Currie | Configuration | Workday | ADP | Cancelled | ADP have identified a new time code is required to support multi positions. This code will only be applicable to RMIT Training ee's. | To ensure correct payment due to different rates across EA's. | TRUE (must explain in Change Control justification) | Medium | Low impact and absorbable. | tba | tba | n/a | n/a |  | tba |  |  | Analysis | Phase 2 | UAT | 2020-04-22 |  |  | Due to new EA being approved, a new CR will be raised to capture all changes required.
151 | Allow Philanthropic Manager to Journal for Gift Related transactions | Fin Accounting | NA |  |  |  | not applicable | CLM | Michelle Paez-Kirkland | Technoology | Manish Pandey | Simon Biddle | Integration | Workday | icertis | Approved | 80 hours of additional Technical effort to provide delta loads of Customer Master Integration. This is more efficient and minimizes the workload in ICM and future proof for increased customer base. This requires RaaS service to be built. | Reduce system integration workload from Workday to icertis ICM. Based on the conversation with ICM team, option 1 is unlikely to get endorsed from their design council. | FALSE | High | Integration design and effort - no expected impact on CLM SIT start date | not applicable | not applicable | Customer master data from workday to icertis | Additional effort on schedule | 80 hours |  | 2020-04-27 | 2020-04-27 | 27/4 - Endorsed and Approved. May need to be assessed again if other higher priority comes in. Deliver for start of Icertis SIT. Update schedule, finalise design, build | Phase 2 | SIT | 2020-04-22 | Program | TBA | ICM is prefer the option 2 as one of their clients has already implemented in this way. Based on the conversation with ICM team, full data load is unlikely to get endorsed from their design council. Delivered for start of July (not start of SIT)
152 | Western Union payment type mapping change | Settlements | SIT2 | 03/07/2020 |  | May be a config change which don't impact data. Addressing CR#146 wil address this CR too | create additional data load template and all required worktag values to be populated | Finance | Omer Bilal | Data | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Pending Approval | Additional data load template required along with all required worktags values to be populated | Position Budget data is loaded via similar Import Budget template with all employee related data to be loaded via worktags. Mapping is required to map Pay Component to Finance GL Accounts | FALSE | Medium | N/A | N/A | N/A | N/A | N/A | N/A | TBC | 2020-05-01 |  | Confirm with data team on requirements and timing. Additional details in attachment | Phase 2 | SIT | 2020-04-22 | Program
153 | Update to FX Bank Reconciliation Rules | Banking | NA |  |  |  | None | Finance |  |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | New | Custom validation to be added to intercompany accounting journals to stop the journal being processed without an intercompany worktag included. | Workday does not automatically populate intercompany affiliate worktags on accounting journals, without the custom validation intercompany balance will be out when running reports. | FALSE | Medium | None | None | None | None | None | [5 empty] | Phase 2 | SIT | 2020-04-23
154 | Fund Sources - Align Detailed Fund Sources to current SAMS / A&I Detailed Funds |  | SIT2 | 03/07/2020 |  | Config workbook change. No ETL impact | EH:- Approved for SIT 2 with no impact | HR | Wendy Draper | Payroll | Renee Teranen | Michael Currie | Configuration | Workday | ADP | Pending Approval | ADP requires a work schedule for casual employees receiving paid leave. This will be managed manually in ADP. All Casual LSL requests will now route to the Payroll partner after the manager to update the work schedule in ADP. | To ensure correct payment for casual paid leave, ADP requires a default Work Schedule. | TRUE (must explain in Change Control justification) | Medium | CK:- An hour or so with low (minimal) impact on integrations | RK:- No impact on HR, finance or cross functional reports. | MP:- As there is a change in the process we will need to update the Absence tab in our HR transaction list to reflect the new workflow. Aside from that, no impact for T&C. | Nil |  |  | This will have minimal impact to HR SIT. 1 additional test case is required to capture the Payroll Partner approval. |  | 2020-05-25 |  | Phase 2 | SIT2 | 2020-04-23 | Workstream |  | Functional impact to route requests to payroll partner after Manager approval for LSL. It will take me about 3 days to build, test and migrate the configuration across the different tenants.
155 | VNM Benefit Plan mapping | Human Resources |  |  | Ruhi |  | Not applicable | Procurement Ops | Lindy Witton |  | Jen Kyle | Brad West | Security | Workday |  | Closed | Refer to the attachment - There are procurement role changes for Australia | Role changes for procurement | FALSE | High | Not applicable | Not applicable | Not applicable | Not applicable | Incorporated into the configuration changes | Not applicable | No impacts | 2020-04-27 | 2020-04-27 | 27/4 - Endorsed and approved. Roles to be updated in Workday for SIT | Phase 2 |  | 2020-04-23 | Program |  | Please refer to the Attachment for details
158 | New Custom Validations for Lease Contracts | Assets | NA |  |  |  | Not applicable | Procurement Ops | Lindy Witton |  | Jen Kyle | Aneta Wielgus | Configuration | Workday |  | Closed | Please refer to the attachment. Procurement changes to be made for Vietnam and RMIT Europe | Refined design change for Vietnam and Spain post P2 Playback - not taking up some aspects for Australia | FALSE | High | Not applicable | Not applicable | Not applicable | Not applicable | Incorporated into |  | No impact as test cases have been updated | 2020-04-27 | 2020-04-27 | 27/4 - Endorsed and Approved. To deliver prior to SIT starting. Configuration changes to be made. Made prior to SIT commencement. | Phase 2 |  | 2020-04-23 | Program |  | Please refer to the attached document for design changes for Vietnam and RMIT Europe
159 | Alternate Supplier Contract Event BP brought back in scope | Assets | NA |  |  |  | N/A | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Security | Workday |  | Approved | Adding the Business Asset Accountant to the “initiating action” list in the create journal BP | This will allow the Business Asset Accountant to make amendments o accounting for certain asset life cycle scenarios | FALSE | Medium | N/A | Impact assessment done on 1-May. No Impact. | N/A | N/A | N/A | N/A | Kainos security testing will required update | 2020-04-27 | 2020-05-04 | 4/5 - Endorsed and Approved. Security for the create journal BP to be updated in all tenants | Phase 2 | SIT | 2020-04-23 | Workstream |  | PMO decision: Approved.
160 | Enabling Spend Category for Expenses | Procurement (Sup Contract, RFQs) | NA |  |  |  | Without these new lease type included. Data cannot load leases according to their schedule | Procurement Ops | Hunter Pool | Finance | Jen Kyle | Aneta Wielgus | Configuration | Workday |  | Closed | Adding two new lease supplier contract types (Straight Line Expense - Variable Payment & Straight Line Expense - Fixed Payment) and changing the setting of the Operating Lease contract types to be able to create assets. | We need to include these two new contract types to allow data to convert legacy lease contracts that exist across two accounting standards | FALSE | High | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-04-27 |  | Approved - 29/4 - Finance provided approval on email from CLM. 27/4 - Procurement to assess the potential impact. Finance to build the new lease contract types and for data to commence the lease contract load | Phase 2 |  | 2020-04-23 | Workstream
161 | Add compensation change step to Parental Leave LOA Request | Absence and Time | NA |  |  |  | There will be no data impacts as a result of this change | HR | Mira Listar |  | Renee Teranen | Michael Currie | Scope | Workday |  | Approved | A number of new reports have been put forward for go-live delivery | As a result of P2 workshops and out of scope integrations a new set of critical reports are required for go-live. Please see attachments for list of reports | FALSE | High | There will be no integration impacts as a result of this change | There will be reporting impacts as a further 10-12 reports are required for go-live | There will be some process and services impacts given that some of the reports are related to out of scope integrations. A meeting has been scheduled for Mon 27/04 to discuss the potential changes etc. | One of the out of scope integrations relate to TRIM. Finance and Procurement stream will need to provide BA to help map out the manual integration requirements for go live. HR BA is currently working on TRIM solution analysis for the HR scope | None | None | There will be some testing impacts given that some of the reports are related to out of scope integrations. A meeting has been scheduled for Mon 27/04 to discuss the potential changes etc. | 2020-04-27 | 2020-04-27 | 27/4 - Endorsed and Approved. CR to be approved and reporting team to analyse reporting requirements and delivery plan for development. Liaise with T&C Michelle on org impacts/effort | Phase 2 | UAT | 2020-04-23 | Program |  | Meetings have taken place with Jyotsna and Rafay on the reports. This will continue from the point that this change request is approved
162 | Remove Tax Review on Intercompany Transactions | Tax | NA |  |  |  | No | Payroll | Andrew Semmens |  | Natalia Hawkins | Matthew Bailey | Integration | Workday | ADP SAP Payroll | Pending Approval |  | Program is used to capture costs for a range of international education programs such as Singapore Institute of Management. Associated costs of running the programs needs to be captured. | FALSE | High | Yes - change the GL interface file from ADP | No - Program is already part of WD reporting | No | Yes - may impact time entry. | TBC | TBC |  | 2020-05-04 | 2020-05-04 | 18/5 - WD integration team haven't done assessment. Testing team to respond. Reporting need to assess off-line. Cost impact to be assessed with both ADP and WD resources | Phase 2 | SIT2 | 2020-04-24 | PCG | PMC 671698 | ADP is aware of the requirement and has confirmed proposed solution is possible
163 | Intercompany Invoicing Tax Expense | Tax | NA |  |  |  | EH:- Approved for SIT 2 | HR | Wendy Draper |  | Renee Teranen | Michael Currie | Configuration | Workday | ADP | Pending Approval | New EA has been approved by the Commission - Various changes required to current configuration | New EA | TRUE (must explain in Change Control justification) | High | CK:- Minor impact with changes less than an hour to complete | RK:- All HR Cross-Functional and 2-3 HR Reports impacted. Impact minimal, can be absorbed. Assumption: no new field added, it is just one EA being added to existing list | MP:- No impacts from a T&C perspective as the implementation / communication of the new EA would be communicated and managed by RMIT training | Finance - mapping new time entry codes (Andrew Semmens) |  |  | This is new and will not have an impact on any of the current SIT scenarios.- JP |  |  | analysis | Phase 2 | SIT2 | 2020-04-24 |  |  | ADP CR has been raised.
164 | New Book Code: Lease Expense | Assets | SIT2 | 12/06/2020 | Simon | Check with Hunter and solution | N/A | Finance | Brian Kiernan | Reporting | Natalia Hawkins | Aneta Wielgus | Reporting | Workday |  | Approved | Requirement for Reporting team to create extracts to the following 6 systems: Blackline, SRS (VN), Project Online (PPM), Bartender, THINK / InformIT (Training), Research Portal. Additional in attachment. | Listing of required reports |  | High | Require provision of any information / requirements that integrations had previously collected for these integrations | Sprint 6 introduced to do these reports. finishing on 22-May. testing team to test after discussion with Brian. | N/A | N/A | N/A | N/A | Ensure that Process include relevant integrations | 2020-05-04 | 2020-05-04 | 4/5 - Endorsed and Approved. Data team to scope out effort.- complete. Finance stream to confirm requirements - underway | Phase 2 | SIT | 2020-04-24 | Program |  | Action - Brian, Sonja and Simon to follow up the testing - conditional aapproval
165 | Spend Category for financial budget to Level 3 | Finance | SIT2 | 03/07/2020 | Rochit | Mapping update for budget extract. May change in future based on analysis and output. Awaiting approval and more information | Data team will have to change their target field to this newly configured custom field labelled "Indigenous Status", once approved. | HR | Snehal Kabra |  | Renee Teranen | Michael Currie | Data | Workday |  | Approved | Diversity & Inclusion team in along with Indigenous Education & Engagement representatives have requested creation of a new custom field for capturing Aboriginal and Torres street islander identifier. This will be an optional field. | Workday delivered field "Race/Ethnicity" cannot be re-labelled and hence can't be repurposed for several reasons outlined in attached paper to support this change.We will also be turning of this standard workday delivered field to avoid confusion. | TRUE (must explain in Change Control justification) | Low | Heads up given to all in daily stand up. data and reporting are the 2 areas where we will have minor impacts. | RK: Impact assessment done on 1-May. 6 to 7 reports will require changes. Minimal effort impact. To be absorbed. | None. | None. | None. | To be determined as per SoW, for building a custom field(Deloitte/ MC to reflect) | a new scenario to be added to our list to ensure testing of this custom field,drop down values and reports. | 2020-05-08 | 2020-05-04 | 4/5 - Endorsed and Approved. PMO Review/decision: Significant challenges raised about maintenance, impacts and going against global solution. Over-ruled, at heart of RMITs core values and reputation damage unacceptable. |  | UAT | 2020-04-27 | Workstream |  | PFA for detailed justification. All efforts were made to avoid any customization in the tenant, however given the sensitivity and our reconciliation commitment it was decided to create new field
167 | Contract value check should not apply to catalogue contracts | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | Not applicable | Procurement Ops | Gavin Patrick | Finance | Jen Kyle | Brad West | Integration | Workday |  | Deferred | Bring into scope one further Punchout as an integration - RS components | Enhance end user experience. Current in scope are all lab supplies organisations. Tech effort of 60 hours it will be offset by the effort to integrate a hosted catalogue, and then integrate this as a Punch Out post go-live. Refer to the attachment | FALSE | High | Yes | RK: Impact assessment done on 1-May. No Impact. | Not applicable | Not applicable | Incorporated into development and configuration changes | Not applicable | None | 2020-05-11 | 2020-05-05 | 18/5 - Backlog. 4/5 - Steven to work with Jen and come back. Further info required back to PMO and Manish. Kick off meeting with Vendor | Phase 2 |  | 2020-04-28 | Program |  | Deferred decision as at 11.05.Refer to the attachement. LifeTech is currently at "risk" as an integration, so this will also act as a good redundancy, so that a minimum of 3 punchouts is delivered, which will be welcomed by Procurement BAU.
168 | Authority Type and Signature Methods updated | Banking | NA |  |  |  | Discussed with Simon Wright (which was communicated to the wider data team) that update is possible during SIT to Customers and Suppliers | Finance | Ben Matters | Supplier, Customer, Company | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Approved | Tax Status tags customers and suppliers with a specific status which enables tax defaulting in more scenarios. | This functionality reduces manual inputs, human error and improves tax reporting. | FALSE | Medium | N/A | RK: Impact assessment done before 5-May. New custom report required to validate master data (company, supplier, customer) associated with new config. Effort has been factored in reporting Sprint 6. Available before SIT. | Finance process impact for creation of suppliers and customers, and then need to communicate tax status so company configuration is updated | N/A |  |  | Test creation of customers and suppliers process, test tax scenarios through customer and supplier invoicing | 2020-05-04 | 2020-05-04 | Meeting to discuss the process of mapping each entity with tax statuses to enable defaulting | Phase 2 | SIT | 2020-04-28
110 | Tax Exports Customer Validation for Customer | Tax | NA |  |  |  | n/a | Finance | Ben Matters | Customer | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Export Tax defaulting requires custom validation to prevent changing tax applicability | This is a small change to further increase the efficiency and accuracy of tax and tax statutory reporting | TRUE (must explain in Change Control justification) | High | n/a | n/a | n/a | n/a | n/a |  | Will need to test the validation, where customers with international ship-to-address should error is the tax applicability isnt AUS Sales Export GST |  | 2020-05-18 |  | Phase 2 | SIT2 | 2020-04-28
111 | Work Schedule - ID Ref Change to identify Country | Absence and Time | SIT2 | 12/06/2020 | Ruhi/ Ken | Dependant on configuration change. | EH:- VN – Crosswalk Change, No ETL Change SP – Identify Spain work schedules separately, Cross Walk Change, No ETL Change. Change can be handled in next cycle of conversion | HR | Wendy Draper | Payroll | Renee Teranen | Michael Currie | Configuration | Workday | ADP | Pending Approval | ADP requires Work Schedules to be Country Specific, this is not required in Workday. To ensure a user selects the correct Work Schedule a V will be added to the naming of the Vietnam Schedules and an S for the Spain schedules. | Integration will fail if a Work Schedule not specific to the Country is selected on Hire or Job Change. | FALSE | Medium | CK:- No impact on integrations | Nil | WD:- Work Instruction required. | Nil |  |  | JP:- We have currently planned 4 Scenarios for a Vietnam in Time Tracking. We will need to revisit the test cases to update. Minimal impact to HR. | 2020-05-25 |  |  | Phase 2 | SIT2 | 2020-04-28 |  |  | Change cannot be made in Workday until ADP have updated the Vietnam schedules. Dhaval has confirmed that changes have been made in ADP
112 | Adjustment to Spain Leave Calculations | Absence and Time | SIT2 | 12/06/2020 | Ken | Ken to request for data. | Approved for SIT 2 | HR | Wendy Draper |  | Renee Teranen | Michael Currie | Configuration | Workday |  | Pending Approval | Spain have provided an update to some pro ration logic and entitlements for various leave types. Details attached. | CR required to ensure correct leave entitlements are calculated and granted in workday. | TRUE (must explain in Change Control justification) | Medium | nil | nil | nil | nil |  |  | System Testing impact only - accrual logic. |  |  |  | Phase 2 | SIT2 | 2020-04-29 |  |  | A&T Functional Impact: this will be based on the outcome of the extent of pro-ration logic we will be building in the system. Effort could range from 1 to 2 weeks to build and test from a configuration perspective.
113 | Bank Rec & First Notice Rule Changes | Finance | NA |  |  |  | NA - Simon Wright Reviewed. | Finance | Sarah Dozortseva | Banking & Settlements | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Approved | Changes to first notice rules. Changes to existing rec rules so that transaction ref ID can be found in addenda and not just bank statement reference. Addition of Bpoint/Bpay rec rule | First notice rules consolidated, one rule encapsulates all of them. Inclusion of addenda removes need to put parsing rules in scope for vietnam (ANZ will not map WD ref ID to ref field, only in addenda) amd enabled auto rec for Bpoint/Bpay | FALSE | Medium | NA - Aashish Manaktala reviewed | RK: Impact assessment done on 1-May. No Impact. | NA | NA |  |  | Less first notice rules to test. Matching rules easier to satisfy and process more efficiently. |  | 2020-05-04 | 4/5 - Endorsed and Approved. | Phase 2 | SIT | 2020-04-29 |  |  | No cross stream objections - approved
114 | Bank Account Configuration - account usages, allowed payment types, integrations | Finance | NA |  |  |  | NA - Simon Wright Reviewed | Finance | Sarah Dozortseva | Banking & Settlements | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Approved | Some changes to allowed payment types, account usages, and enabled integrations on the bank accounts | With integrations now built, request from integrations team to enable them on bank accounts for SIT testing. Payment types and account usages corrected to allow for direct customer deposits and required integrations | FALSE | High | Necessary for SIT testing - Aashish Manaktala | RK: Impact assessment done on 1-May. No Impact. | NA | Required by Customer Revenue to record deposits properly (Ryan Auteri). Facilitates testing for integrations. |  |  | Changes required for integrations SIT testing |  | 2020-05-04 | 4/5 - Endorsed & Approved. | Phase 2 | SIT | 2020-04-29 | Program |  | Approved
115 | Fixed casual rate for a casual academic | Compensation | SIT2 | 19/06/2020 | Kathleen | Mapping and ETL change only | Minor impact to map these casual academics both on secondary and project positions | HR | Tom Koola | ADP | Renee Teranen | Michael Currie | Integration | Workday | ADP | In Analysis | Fixed casual rate for a casual academic | Agreed Rates for Casual Academics. Currently integration and time tracking configuration does not account for the 100 or so casual academics are paid a fixed rate (as a primary or a secondary position) | TRUE (must explain in Change Control justification) | Medium | Main impact as the integration does not pick this cohort for a fixed rate | [RK]: Position paper awaited. Then will do impact assessment. | Yet to be determined based on solution | Finance for project costing | Minor - based on solution | NA | Once solution is finalised and built, it will need to be tested for both scenarios (primary and secondary position) with agreed rates | 2020-05-08 | 2020-05-15 |  | Phase 2 |  | 2020-04-30 | Workstream
116 | New Project Role - Project Creator | Projects | NA |  |  |  | N/A | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Security | Workday |  | Approved | A new role for projects called "Project Creator". This role will be held by someone in the service center to create the offline approved project in workday and assign initial roles as per the service request form | To accommodate the service now process and to ensure Project Financial Analysts are selected per project rather than inherited from the hierarchy | FALSE | Medium | N/A | RK: Impact assessment done on 1-May. No impact. May be very minimal impact to 1 Cross-Func report. | N/A | N/A | N/A | N/A | N/A | 2020-05-04 | 2020-05-04 | 4/5 - Endorsed and Approved - To work with Harshit to create the roles in the appropriate tenants, apply the accurate security and update workbooks | Phase 2 | SIT | 2020-04-30 | Workstream
117 | Capex Settlement to WIP accounts - Replace Project Group with Optional Project Hierarchy | Projects | SIT2 |  |  | To check with Rochit | Remap Project Group to Project Hierarchy | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Approved | Remove WIP classifications in Project Groups. Add WIP classifications to Optional Project Hierarchy. This will allow us to drive salaries to the correct WIP account using an allocation | ADP does not have the ability to post to WIP accounts. The only way to sweep the payroll journals to WIP automatically is to run an Allocation. The Allocation Cannot use Project Group as a driver to allocate to PPE / Intangible. | FALSE | Medium | Alteration to Project Labour Costing Integration (WD – WD integration) | RK: Impact assessment done on 1-May. No impact. May be very minimal impact to 1 Cross-Func report. | N/A | N/A | N/A | N/A | N/A | 2020-05-04 | 2020-05-11 | 11/5 - Endorsed and Approved. SIT2. Create the new optional project hierarchies in the relevant tenants. Data to remap project groups using new optional project hierarchy values. | Phase 2 | SIT | 2020-04-30 | Workstream |  | PMO update: Integration can be done by SIT. Part 1 of request. Will need to be investigated in Payroll. Offline investigation. Email back to group.
118 | Tax Defaulting for Intercompany Transactions (AUS - VNM) update | Tax | SIT2 |  |  | Simon to check | N/A | Finance | Ben Matters | Revenue | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Update revenue category tax mapping for intercompany invoicing with RMIT Vietnam | Natalia and Khanh agreed on changing tax flow - in compliance with Ryan's (Tax Auditor) advice | TRUE (must explain in Change Control justification) | High | N/A | N/A | N/A | N/A | N/A |  | Testing will need to update scripts to ensure validation of defaulting is correct | 2020-05-11 | 2020-05-11 |  | Phase 2 | SIT2 | 2020-05-04 | Workstream
119 | New BP - Cash Advance Repayment (VNM Specific) | Expenses |  |  |  |  | N/A | Finance | Ben Matters |  | Alex Dieng | Aneta Wielgus | Configuration | Workday |  | Cancelled | Vietnam require a new bp to capture the repayment of a cash advance to an employee | Ensures the E2E process of cash advances flows efficiently in workday | FALSE | Medium | N/A | N/A | New L4 process to be created and added into L3 | N/A | N/A |  | Test team will need to add another script to test out this additional BP | 2020-05-11 | 2020-05-04 |  | Phase 2 | SIT | 2020-05-04 | Workstream
120 | RMIT Spain - Supplier Payment File to La Caixa Bank | Finance | NA |  |  |  | NA | Finance | Andrew Semmens | Settlements | Natalia Hawkins | Deloitte | Integration | Workday | La Caixa Bank Portal | Pending Approval | RMIT Spain - Supplier Payment File to La Caixa Bank | File format required by La Caixa is an integration file, not a report. ISO20022 file format, | FALSE | High | Yes - requires a file to be created in ISO20022 file format, | RK: Impact assessed on 11-May. Already factored into WD Fin / Proc Sprint 6 | This integration will align settlement processes across the RMIT group. Also reduce workarounds and associated risk of loading manual payments | NA | TBC | TBC | TBC | 2020-05-11 | 2020-05-11 | 18/5 - Limited capacity for any further integrations. Unsure of volumes and FTE impacts. High impact to have a manual solution - will result in significant FTE impact. Only one person in Spain to process each manual transaction through. Wait for PMO to update the prioritisation process for backlog Wait 2 weeks for the tech team to reassess the effort. DeEcision pending | Phase 2 |  | 2020-05-04 | Workstream |  | Is required in order to pay suppliers in Spain
121 | VN Benefit - Update eligibility of dependents | Compensation | SIT1 |  |  |  | Yes, Data Team is aware of this | HR | Chi Nguyen |  | Renee Teranen | Michael Currie | Configuration | Workday |  | Approved | Update eligibility for dependents of both International & Local healthcare (details sent to Felix) | Confirmation from VN Team after Felix and Data Team was checking the eligibility | FALSE | Low | No | RK: Impact assessed on 11-May. NA. | No | No | No | No |  | 2020-05-11 | 2020-05-11 | 11/5 - Endorsed and Approved. Likely for SIT2. Update Benefit config workbook | Phase 2 | SIT | 2020-05-04 | Workstream |  | Update on the eligibility rule of dependents of employees into health cover. The previous requirements were incorrect (identified during SIT data conversion). Configuration for SIT updated. There is no impact to other streams.
122 | New Role - Project Portfolio Manager | Projects | NA |  |  |  | N/A | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Security | Workday |  | Approved | The addition of the user-based security role: Project Portfolio Manager. | The aim was to use an existing role to cater for the management of Portfolios however workday only allows Project Portfolio Managers to create and manage protfolios | FALSE | Medium | N/A | RK: Impact assessed on 11-May. No impact. May be some security changes required, minimal impact / effort. | N/A | N/A | N/A | N/A | Confirm Project Portfolio Manager is included for all portfolio related test cases | 2020-05-11 | 2020-05-11 | 11/5 - Endorsed and Approved. To assign the new role to the correct domains Assume SIT 2. SIT1 if possible. Testing impacts considered. ​ ​ | Phase 2 | SIT | 2020-05-05 | Workstream |  | Harshit has already been advised and he has said there is no impact for him
123 | System warning/notification for inactive suppliers | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | NA | Procurement Ops | Daniel Chirau | Finance | Jen Kyle | Brad West | Configuration | Workday | NA | Approved | New validation/configuration for a system notification to be genarated when making a supplier in-active. Notification to be generated if the supplier belongs to a panel group or has an open contract. | This will stop contracted suppliers from being deactivated before the contract end date. I believe similar validation exists when blocking or deactivating suppliers with open transactions." | FALSE | High | NA | RK: Impact assessed on 11-May. No impact. | NA | NA | Nil | NIL | Test case for making supplier inactive to be updated | 2020-05-11 | 2020-05-11 | 11/5 - Endorsed and Approved. Will be part ofSIT2. Configuration to be undertaken | Phase 2 | SIT | 2020-05-06 | Program
124 | AHBT Templates - Vietnam and Corporate Credit Cards; CC 1st notice rules | Banking & Settlements | NA |  |  |  | NA - Simon Wright Reviewed | Finance | Sarah Dozortseva |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Approved | AHBT templates for new Vietnam Cash Advance process. Added missing AHBT templates for credit cards and corresponding 1 st notice rules for RMIT Online/Training/Spain. Added Corprorate Credit Card field as additional worktag for AHBT | enables automatic reconciliation and correct worktags on CC AHBTs. Allows for recording of cash when employee returns unspent cash advances. | FALSE | Medium | NA - Aashish Manaktala | RK: Impact assessed on 11-May. No impact. | NA | NA | NA | NA | A few additional first notice rules. |  | 2020-05-11 | 11/5 - Endorsed and Approved. . WIll change testing of bank reconcilliation rules Will impact VN only, can proceed with the AU testing VN changes into SIT 2. ​ | Phase 2 | SIT | 2020-05-06 | Workstream
125 | Remove Project Service Based Requisition | Procurement (Sup Contract, RFQs) |  |  |  |  | NA | Procurement Ops | Bipin Singh | Finance | Jen Kyle | Brad West | Configuration | Workday | NA | Closed | This is used to request services for different project tasks and phases. These cant be auto-sourced . Manual intervention required to move a req to PO. All other requisitions at RMIT can be auto-sourced. A non-catalogue requisition type can be used. | Remove the requirement for manual intervention of moving from a Req to PO and a non catalogue requisition type can be used. | FALSE | High | NA | RK: Impact assessed on 11-May. May impact 1 Cross-Fun Fin / Proc report | NA | NA | Incorporated into development & configuration changes | NA | Test cases to be updated | 2020-05-11 | 2020-05-11 | 11/5 - Endorsed and Approved. Part of SIT2 test cycle. Configuration for Proc Ops to be updated | Phase 2 |  | 2020-05-06 | Program
126 | Payment Release BP configuration updated | Banking & Settlements | NA |  |  |  | NA - Simon wright | Finance | Sarah Dozortseva |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Approved | Removed redundent document delivery steps, configured existing integration step to work with existing integrations | changes made per guidance from Integrations team | FALSE | High | Required for integrations to be triggered after completion of settlement run. Necessary to enable operation of integrations and testing | RK: Impact assessed on 11-May. No impact. | NA | NA | NA | NA | Required for testing of integrations |  | 2020-05-11 | 11/5 - Endorsed and Approved. Testing SIT1. | Phase 2 | SIT | 2020-05-06
127 | Record UNSPSC to Spend category mapping in Workday | Procurement (Sup Contract, RFQs) |  |  |  |  | NA | Procurement Ops | Jen Kyle | Finance | Jen Kyle | Brad West | Configuration | Workday | NA | Closed | "Record UNSPSC to Spend category mapping in Workday Needed to support auto population of spend category through a punch out requisition" | Needed to support auto population of spend category through a punch out requisition | FALSE | High | NA | RK: Impact assessed on 11-May. Will impact 1 Cross-Fun Fin / Proc report | NA | NA | Incorporated into configuration changes | Nil | Na | 2020-05-11 | 2020-05-11 | 11/5 - Endorsed and Approved.Configuration to be completed | Phase 2 |  | 2020-05-06 |  |  | Within Proc Ops
128 | Custom validation to warn user to select ‘catalogue’ when creating a catalogue contract, | Procurement (Sup Contract, RFQs) | NA |  |  |  | NA | Procurement Ops | Bipin Singh |  | Jen Kyle | Brad West | Configuration | Workday | NA | Approved | This warning is not WD default and if missed the user cannot go back and edit | This cannot be a critical error / validation as punch-out catalogues are not linked to the contract via the same way. | FALSE | High | NA | RK: Impact assessed on 11-May. No impact. | NA | NA | Incorporated into configuration | NA | NA | 2020-05-11 | 2020-05-11 | 11/5 - Endorsed and Approved. SIT1 |  |  | 2020-05-06 | Program
129 | Instrument Free entitlements | Absence and Time |  |  |  |  | nil | HR | Wendy Draper |  | Renee Teranen | Michael Currie | Configuration | Workday |  | Approved | Increase to entitlements for Instrument Free employee to align with Agreement covered collegues. | Alignment between Agreement bound employees and Instrument Free employees | TRUE (must explain in Change Control justification) | Medium | nil | RK: Impact assessed on 11-May. No impact. | nil | nil | nil |  | nil - will be covered off in Functional unit testing |  |  | ​15/5 - Approved. Will Footner advised recommedation for prioritising for SIT2. CR prioritised relates to leave. RMIT applies leave entitlements into RMIT training, will bring them inline with the EA. Renee has been advised there is no impact anywhere Payroll have allowed for this revised set up No impacts raised anywhere else. Data, reporting and integration - Simon wants to confirm when the config changes will happen - SIT2 may be possible. Testing - will go into UAT, no functional impact. Action - Renee to follow and circle back with clarification on timing for the config updates. Keep as pending approval until clarified | Phase 2 | UAT | 2020-05-06 |  |  | Impact to Absence functional area only. UAT Workbook updated with entitlements.
130 | Update of Tax related custom validation on Requisition BP | P2P (R2P2R, I2P, Supplier Record) |  |  |  |  | nil | Finance | Ben Matters | Procurement | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Cancelled | Update of Tax related custom validation on Requisition BP to enforce Vietnam Specific requirement for PIT and remove acquisition tax validation from requisition. Acquisition tax codes will be controlled on the supplier invoice only. | updates to tax requirements in P2P processes | FALSE | Medium | nil | RK: Impact assessed on 11-May. No impact. | nil | BP requisition is owned by Procurement. Communication has been sent to them to further explain the justification |  |  |  |  | 2020-05-11 |  | Phase 2 | SIT | 2020-05-06 | Workstream |  | Cancelled - no longer required as PIT is not on requisition and therefore will only be controlled on supplier invoices
131 | Vietnam Student Customer Management | Finance | NA |  |  |  | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Security | Workday |  | Approved | Allow a Vietnam Customer Record Manager to Update Vietnam Students in Workday Directly | Current Assumption was to do everything via WebService (Flat File Uploads) - but need to extend to do single updates within Workday Directly - No Role can do this for students | FALSE | Medium | N/A | RK: Impact assessed on 11-May. No impact. | N/A | N/A | N/A |  | New role to test access |  | 2020-05-11 | 11/5 - Endorsed and Approved. SIT2. Add Security Group Low impact change. | Phase 2 | SIT | 2020-05-07
132 | Changes to Procurement spend categories | Procurement (Sup Contract, RFQs) |  |  |  |  | NA | Procurement Ops | Lindy Witton | Finance | Jen Kyle | Brad West | Configuration | Workday | NA | Closed | 4 spending categories to be deleted as requirements met by assets module. 1 spend category to be renamed. 1 new spend category. Refer attachment | Spend categories to be updated. New spend category for $2m spend for RMIT Exhibitions. There is no equivalent Spend Category or way to classify this spend | FALSE | High | NA | RK: Impact assessed on 11-May. Will impact 1 Cross-Fun Fin / Proc report | NA | NA | Incorporated into development & configuration changes | NA | Test cases to be reviewed | 2020-05-11 | 2020-05-11 | 11/5 - Endorsed and Approve.​ Configuration to be updated. SIT1. | Phase 2 |  | 2020-05-07 | Program |  | Refer to the attachment for details
133 | Retained Earnings - Allowing Gift Worktag | Finance | NA |  |  | Need to check if a new CR comes through to bring opening balance for Gifts | N/A - There is no Opening Balance load currently scoped - Potential new CR | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Approved | Enabling the Gift Worktag on Retained Earnings allows reporting on the WoL balance for Gifts | Need to report WoL gift balances to donors - current workaround is very manual - this will automate the process | TRUE (must explain in Change Control justification) | Medium | N/A | RK: Impact assessed on 11-May. Impacted couple of WD Fin / Proc reports. Already adjusted. Being tested now. | Reduced Effort | N/A | N/A | N/A | Need to Validate Retained Earnings Impact on Gift through the Roll Over BP and any Journals to Gifts |  | 2020-05-11 | 11/5 - Endorsed and Approved. Update Configuration Reports are being adjusted, review testing scenarios and push those to SIT2. ​ | Phase 2 | SIT | 2020-05-07
134 | DA Outcome - Amend Minimum Threshold for Customer Write-Offs | Finance | NA |  |  |  | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Approved | Add an minimum approval threshold for Bad Debt Write Offs - Any approval below $100 will not require an approval/review | Workday DA Recommended ¦ Reduction of Effort ¦ Matches the automatic writeoff process | FALSE | Low | N/A | RK: Impact assessed on 11-May. No impact. | N/A | N/A | N/A | N/A | Amended Bad Debt Write Off BP |  | 2020-05-11 | 11/5 - Endorsed and Approved. Change in Workday Testing scenarios will be pushed into SIT 2 ​ | Phase 2 | SIT | 2020-05-07
135 | Update to have asset usage on Campus location type to enable searching when issusing/transferring an asset | Finance | SIT2 |  |  | Mapping change in Location extract | Update to data logic to enable location type 'Campus' for business asset (informed Simon Wright and ok with change) | Finance | Aimee Mensink | Integrations | Natalia Hawkins | Aneta Wielgus | Integration | Workday |  | Pending Approval | Update location conversion logic to allow Business Asset to be enabled on Campus locations coming from Archibus. Custom validation on asset BPs to not allow an asset to be issued or transferred to a campus. | To enable user to each for location when issuing/transferring an asset | FALSE | Medium | Update to integrations logic to enable location type 'Campus' for business asset (informed James Garner and ok with change) | nil | nil | nil | nil | nil | will allow assets test cases to be executed in a simpler way |  |  |  | Phase 2 | SIT | 2020-05-07
136 | iCertis Descope - Customer Contract BP Documentation | Finance | NA |  |  |  | N/A | Finance | Ryan Auteri | CLM | Natalia Hawkins | Aneta Wielgus | Process | Workday | iCertis | Pending Approval | Require Customer Contract BP documents to change wording to ensure manual creation only, iCertis is no longer the source of contracts. Finance will require an approved contract in order to enter and bill from the system | iCertis Descop | FALSE | Medium | N/A | More general impact till Workday config changes doesn't become clear. If there are new reports required due to Icertis descope, that may be a risk. | N/A | N/A | N/A | N/A | iCertis impacts to be determined |  |  | Test Cases to be amended, Documentation to be updated | Phase 2 | SIT | 2020-05-09
137 | Two templates for Performance Review and Calibration process | Talent |  |  |  |  | No impacts | HR | Dharitri Desai | Performance | Renee Teranen | Michael Currie | Process | Workday |  | Cancelled | To meet varying calendar dates and population performance review and calibration process will run over two separate timeframes | There is a requirement to run a performance cycle for non executives and executives at separate performance cycles thus a need to create a new performance plan template | FALSE | High | No impacts | No impacts | Change and training will need updating | No impacts | No impacts | No impacts | The performance template should be the same just different dates for the various stage gates |  | 2020-05-18 | Demo a prototype, understand Core identifiers for the VCE executive group that get calibrated in Dec | Phase 2 | UAT | 2020-05-11 | Workstream |  | Emails attached for details
138 | Two templates for Performance Review and Calibration process | Talent |  |  |  |  | None | HR |  | Performance | Renee Teranen | Michael Currie | Process | Workday |  | Cancelled | To meet varying calendar dates and population performance review and calibration process will run over two separate timeframes | To meet varying calendar dates and population performance review and calibration process will run over two separate timeframes |  | High | None |  | Change and training will need updating | None | None |  |  |  | 2020-05-05 | Demo a prototype, understand Core identifiers for the VCE executive group that get calibrated in Dec | Phase 2 | UAT | 2020-05-11 | Workstream |  | Emails attached for details
139 | Two templates for Performance Review and Calibration process | Talent |  |  |  |  | None | HR |  | Performance | Renee Teranen | Michael Currie | Process | Workday |  | Cancelled | To meet varying calendar dates and population performance review and calibration process will run over two separate timeframes | To meet varying calendar dates and population performance review and calibration process will run over two separate timeframes |  | High | None |  | Change and training will need updating | None | None |  |  |  | 2020-05-05 | Demo a prototype, understand Core identifiers for the VCE executive group that get calibrated in Dec | Phase 2 | UAT | 2020-05-11 | Workstream |  | Emails attached for details
140 | Review Payment Acknowledgement BP - Initiating security changed | Banking & Settlements | NA |  |  |  | NA | Finance | Sarah Dozortseva |  | Natalia Hawkins | Aneta Wielgus | Security | Workday |  | Pending Approval | Removed Cash Manager and Accountant from initiating action, so only Settlement Specialist can assign acknowledged payment to worker for review | Now that the scope of the payment acknowledgment integration has been confirmed, the BP was reviewed to align with RMIT processes. Cash Manager and accountant roles were hangover from WD delivered config. | FALSE | Low | NA | NA | Initating role restricted to Settlement Specialist, process remains the same | NA | NA | NA | Initating role restricted to Settlement Specialist, process remains the same |  |  |  | Phase 2 | SIT | 2020-05-11 | Workstream
141 | Update to Ad Hoc Bank Transaction BP | Banking & Settlements | NA |  |  |  | NA | Finance | Sarah Dozortseva |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Added bank reconciliation specialist to initiating security groups. AHBT with Purpose of FX Gain/Loss will now bypass approvals. | Bank Rec Specialist can already raise AHBT through manual reconciliation dashboard- added for sake of consistency. Purpose added as part of new WU FX solution | FALSE | Medium | NA | NA | Improves ease of use for reconciliation | NA | NA | NA | Bank rec specialist can now raise AHBT using "Create ad hoc bank transaction" task as well as through the manual reconciliation dashboard |  |  |  | Phase 2 | SIT | 2020-05-12 | Workstream
142 | Ad Hoc Payments - mandate payee email address in 'Alternate Name' field to facilitate AHP remittance advice | Settlements | NA |  |  |  | no impact, no data conversion for ad hoc payees | Finance | Aimee Mensink | Integrations | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Pending Approval | Ad Hoc Payments - mandate payee email address in 'Alternate Name' field to facilitate AHP remittance advice. Also update the integration logic from SAMS to populate email address for students and help text for AHP in the user interface | to facilitate remittance advise requirement | FALSE | High | update to integration logic to populate SAMS student email address in 'Alternate name field'. Tracey has confirmed SAMS are happy to provide. Aashish has been consulted | no | no | no | no | no |  |  |  |  | Phase 2 |  | 2020-05-12 | Workstream |  | update to be made for SIT1 to allow integration for remittance advise to work
143 | Supplier Invoice Request BP to be brought into scope | P2P (R2P2R, I2P, Supplier Record) | NA |  |  | Need to check the scope | no | Finance | Andrew Semmens |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Pending Approval | Bring back BP: Supplier Invoice request to accommodate non-invoice payments to registered suppliers ie. donations. | Supplier invoice request will replace a proposed Service Now form. | FALSE | Medium | no | no | yes, brought back in scope. | no | no | no |  | 2020-05-26 |  |  | Phase 3 - Advanced HR | SIT | 2020-05-12 | Workstream |  | Originally this BP taken out of scope as the ad hoc payment functionality was going to be used more extensively. Given this has now been scaled back, this BP is now required.
144 | Update Deferred Revenue Posting | Finance | NA |  |  |  | N/A | Finance | Ryan Auteri |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Update Deferred Revenue Accounts based on Revenue Categories | Deferred Revenue is currently not split by revenue category - Audit Requirement | TRUE (must explain in Change Control justification) | High | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Phase 2 | SIT | 2020-05-12
145 | Creation of custom field to capturing Employee's Indigenous country or Indigenous Nation group (personal information field) | Human Resources |  | 12/06/2020 | Kathleen | Same as 107 | No impact as we do not have this data in BAU/SAP/HRMS, so no conversion required. | HR | Snehal Kabra | Core | Renee Teranen | Michael Currie | Configuration | Workday |  | Pending Approval | Diversity & Inclusion team along with Indigenous Education & Engagement representatives have requested creation of a new custom field for capturing Indigenous country or Indigenous Nation group .It’s an optional field. | Workday delivered field "City of Birth" cannot be re-labelled and hence can't be repurposed for several reasons outlined in attached paper to support this change. | TRUE (must explain in Change Control justification) | Medium | No integration impacts as this field will not be in fed to any +1 down stream systems. | SK: Impact assessment to be done. 6 to 7 reports will require changes. Minimal effort impact. To be absorbed. | No impact, but to be involved in communication to do a campaign too in the lead up to and post launch and help out D&I team | No Impact | None, can be accomodated for SIT Cycle 2 or UAT | To be determined as per SoW, for building a custom field(Deloitte/ MC to reflect) | a new scenario to be added to our list to ensure testing of this custom field,drop down values and reports. | 2020-05-22 | 2020-05-22 |  | Phase 2 | UAT | 2020-05-12 | Workstream |  | PFA for details. All efforts were made to avoid any customization in the tenant, however given the sensitivity and our reconciliation commitment it was decided to create new field.A brainstorm idea on WD community is also raised(including CR #107).
146 | Removal of Wire Payment Type - RMIT Aust Entities & RMIT Indonesia | Settlements | SIT2 |  |  | Mapping change and build | Yes - remove payment type Wire on the entities described above | Finance | Andrew Semmens |  | Natalia Hawkins | Aneta Wielgus | Data | Workday |  | Pending Approval | Remove Wire payment type from RMIT Australia Entities & RMIT Indonesia. | As there is now a confirmed approach with Western Union, there is no value in retaining wire as an allowed payment type outside of RMIT Vietnam. It was initially set up in case some international payments would be processed through CBA. | FALSE | Medium | NA | NA | NA | NA |  |  | NA - only testing Western Union integration |  |  |  | Phase 2 | SIT | 2020-05-12 | Workstream
147 | Remove custom validations in contract creation and amendment BPs (icertis descope) | Procurement (Sup Contract, RFQs) |  |  |  |  | NA | Procurement Ops | Jen Kyle |  | Jen Kyle | Brad West | Configuration | Workday |  | Closed | Remove custom validations of contract creation and amendments to allow all contracts to be created and amended in Workday | With descoping of icertis, all supplier contract types required to be created/amended in Workday manually. | FALSE | High | NA | NA | NA | NA | NIL | NA | Testing impacts will be included with icertis descoping activities | 2020-05-22 | 2020-05-22 | 20/5 - Approved over email. Bipin sent to Natalia, Simon, (Chuan), and Eric. | Phase 2 | SIT1 | 2020-05-13 | Program
148 | Procurement Security Roles changes (Specialist Buyer role) | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | NA | Procurement Ops | Jen Kyle |  | Jen Kyle | Brad West | Security | Workday |  | Pending Approval | Update Specialist Buyer security role based on review completed to ensure alignment to RMIT Procurement configuration | The Specialist Buyer role is a custom role for RMIT and was a duplicate of the standard Workday Buyer role. The changes are to remove items that are not appropriate for Specialist Buyers. | FALSE | High | NA | NA | NA | NA | Incorporated into configuration changes | NIL |  | 2020-05-18 |  |  | Phase 2 | SIT2 | 2020-05-13 | Program |  | Refer to the attachment
149 | Provide ability for Procurement Administrator to manage Supplier Groups | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | NA | Procurement Ops | Jen Kyle |  | Jen Kyle | Brad West | Security | Workday |  | In Analysis | During P2 recommended for Proc BAU to utilise Supplier Groups to manage Panels & CSR classifications. Current security roles do not allow Procurement to manage Supplier Groups only for new suppliers. Need to change supplier groups, audit reporting. | Panels will require infrequent changes and raised by Proc BAU. Panel config will also require other complex config. CSR classifications will require more frequent changes as Procurement work towards updating the groups for existing suppliers. | FALSE | High | NA | NA | NA | NA | Incorporated into configuration changes | NIL | Use cases already exist | 2020-05-18 |  |  | Phase 2 | SIT | 2020-05-13 | Program |  | There are 95 supplier groups, of which 93 relation to Procurement requirements and 2 relate to Finance requirements.
150 | Contingent workers removed from Expense Report Business Process in Workday | Expenses | NA |  |  |  | n/a | Finance | Ben Matters | Contingent Worker | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Decision made to not allow contingent workers to raise expense reports in workday. Therefore the Expense Report Event Business Process will need to be changed to remove the contingent worker security group | If this isn't changed then contingent workers who have access to workday will be able to submit expense reports in system and be invoiced for expenses - allowing potential for double dipping for expense reimbursement | FALSE | High | n/a | n/a | Contingent workers no longer included in the L4 BP Expense Report Event in workday | No contingent workers can claim / submit expenses in workday | n/a |  | No longer have to test expenses for contingent workers through the expenses module in workday | 2020-05-11 | 2020-05-18 |  | Phase 2 |  | 2020-05-13 | Workstream
151 | Allow Philanthropic Manager to Journal for Gift Related transactions | Fin Accounting | NA |  |  |  | N/A | Finance | Ryan Auteri | Customer / Gifts | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Enables the A&P team to enter gift journals themselves, rather than manually submitting and having the finance team review and enter | Effort Reduction | FALSE | Medium | N/A | N/A | N/A | N/A | N/A | N/A | New test script for amended BP |  |  |  | Phase 2 | SIT | 2020-05-13
152 | Western Union payment type mapping change | Settlements | TBD |  |  | May be a config change which don't impact data | NA | Finance | Andrew Semmens |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | In Analysis | Mapping of "Western Union" to change from "Wire" to "EFT" | This allows payments to be grouped for reconciliation purposes. Makes manual reconciliation of FX payments more manageable for Bank Rec Specialist | FALSE | Medium | Potential impact on integration. Preliminary testing shows no inpact-will need further analysis from integrations team to ensure it will not break current configuration. | NA | NA | NA | NA | NA | NA |  |  |  | Phase 2 | SIT | 2020-05-13 | Workstream
153 | Update to FX Bank Reconciliation Rules | Banking | NA |  |  |  | NA | Finance | Sarah Dozortseva |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | In Analysis | Existing FX matching rules will now only be in scope for Vietnam. New 1-many matching rule will now apply for AUD payments via WU. New Suggest rule will apply for FX payments via WU | Updates to align with new Western Union Integration solution | FALSE | Medium | In line with new WU integration solution | NA | NA | NA |  |  | New rules will need to be tested |  |  |  | Phase 2 | SIT | 2020-05-13 | Workstream
154 | Fund Sources - Align Detailed Fund Sources to current SAMS / A&I Detailed Funds |  | SIT2 |  |  |  | Only IDs are changing - Implement in SIT2 | Finance | Ryan Auteri |  |  |  |  | Workday |  | Pending Approval | Align Fund Sources to the Detailed Fund Sources, and Broad Fund Hierarchy as provided through meetings with all relevant stakeholders | Alignment of Fund Sources throughout the University's Systems | TRUE (must explain in Change Control justification) | High | N/A - SAMS sends fund source, no requirement to build a mapping table (less effort) | 1 Workday FIn / Proc and 1 Cross-Func report impacted. Minimal impact. | N/A | N/A | N/A | N/A | SAMS test scripts have not been written yet - so will be captured there |  |  |  | Phase 2 | SIT | 2020-05-13 |  |  | Once approved - this needs to be raised in PMC as an FDM Design Decision
155 | VNM Benefit Plan mapping | Human Resources |  |  | Ruhi |  | No | HR | Chi Nguyen | Payroll | Renee Teranen | Michael Currie | Integration | Workday | ADP | Pending Approval | Benefit Plans on Workday to mapping to ADP (mapping codes will be updated on VN DD) including VNM Local Insurance, VNM International Insurance and VNM Dental plans. | It's been come up that there's a gap between WD-ADP mapping about Benefit (Medical Insurance), so currently no integration has been built for this. The requirement for integration is migrating the annual insurance premium per employee to ADP. | FALSE | Medium | Yes. Erick P was across this. | No | No | No | No | No |  |  |  |  | Phase 2 | SIT | 2020-05-13 | Workstream |  | This CR is raised after a meeting between Erick P, Felix, Tom, ADP Qi and myself
156 | Supplier invoice, custom validation. Header contract populated, line empty. Ask user to populate line | Finance |  |  |  |  | nil | Finance | Komal Laddha |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Cancelled | custom validation to aid user to select contract on line for supplier invoice | to reduce error for user thinking they have linked line to the contract but have not |  |  | nil | nil | nil | nil | nil | nil |  |  |  |  | Phase 2 | SIT | 2020-05-13 | Workstream |  | cancelled: WD functionality has been deemed sufficient for this requirement. Supplier invoice adjustment when Original invoice was against a Contract and there was no PO in place. The APDES should also populate contract # in the line & not just header.
157 | 2. Hard stop when someone is deactivating a supplier which has open transactions on their ledger | Finance |  |  |  |  | nil | Finance | Komal Laddha |  | Natalia Hawkins | Aneta Wielgus | Process | Workday |  | Cancelled | custom validation if a supplier invoice has not been paid and the supplier is being made inactive | custom validation to ensure all suppliers are paid before being made inactive | FALSE | Medium | nil | nil | nil | nil | nil | nil |  |  |  |  | Phase 3 - Advanced HR | SIT | 2020-05-13 | Workstream |  | WD functionality deemed adequate
158 | New Custom Validations for Lease Contracts | Assets | NA |  |  |  | N/A | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | The inclusion of two new custom validations for supplier contracts in relation to leases. 1)Total contract amount for Straight Line Leases must not be greater than $5000. 2)Expense recognition method for leases must be number of days | We need these validations to ensure users adhere to the RMIT capitalization policy and the expense recognition calculation method for RMIT | FALSE | Medium | N/A | N/A | N/A | N/A | N/A | N/A | Added test scripts for the new validations | 2020-05-18 | 2020-05-18 |  | Phase 2 |  | 2020-05-14 | Workstream
159 | Alternate Supplier Contract Event BP brought back in scope | Assets | NA |  |  |  | N/A | Finance | Hunter Pool |  | Jen Kyle | Aneta Wielgus | Configuration | Workday |  | Pending Approval | To accommodate for the load of lease contracts across two standards, Workday functionality requires the Alternate Supplier Contract Event BP to be brought back in scope | Without this BP, leases across two accounting standards and leases for Vietnam accounted in the AASB book will not be possible | TRUE (must explain in Change Control justification) | High | N/A | N/A | N/A | N/A | N/A | N/A | New test cases for added business process | 2020-05-25 | 2020-05-25 |  | Phase 2 | Prototype 1 | 2020-05-15 | Workstream
160 | Enabling Spend Category for Expenses | Procurement (Sup Contract, RFQs) | NA |  |  |  | N/A | Procurement Ops | Ben Matters | Expenses | Jen Kyle | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Spend Category SC_10469 - Labour Hire - Recruitment Related Advertising Fees is needed for expenses but not yet enabled for the expenses module. This finance requirement has been communicated by Alex to Lindy for sign-off. | If the spend category is not enabled for expenses then an expense item can not be created and a transaction of this nature can not be expensed | FALSE | Medium | N/A | N/A | N/A | N/A | N/A |  | Update test scripts with additional expense item | 2020-05-25 | 2020-05-25 |  | Phase 2 | SIT | 2020-05-18 | Workstream
161 | Add compensation change step to Parental Leave LOA Request | Absence and Time | NA |  |  |  | nil | HR | Wendy Draper | Compensation | Renee Teranen | Michael Currie | Configuration | Workday |  | Pending Approval | There is a requirement for a comp change for Parental Leave when an employee has not reached 3 years of service. Also new reason code 'Parental Leave' in compensation. | Only HR Central Payroll have access to make Comp changes, therefore this additional step is needed in the request LOA BP. Without this step, the employee would not be paid correctly. | TRUE (must explain in Change Control justification) | Medium | nil | nil | Work Instructions required. | nil | nil |  | nil |  |  |  | Phase 2 | SIT | 2020-05-18 |  |  | Only impacts Absence & Time functional area + Compensation
162 | Remove Tax Review on Intercompany Transactions | Tax | NA |  |  |  | n/a | Finance | Ben Matters | Revenue/Procurement | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Remove Tax Review on Intercompany Transactions for both Customer invoices and supplier invoices | These transactions are consistent and have limited number of revenue / spend categories, as such tax less complicated and not in need of analysis by the tax team | FALSE | Medium | n/a | n/a | n/a | n/a | n/a |  | Update test scripts | 2020-05-25 | 2020-05-25 |  | Phase 2 | SIT2 | 2020-05-19
163 | Intercompany Invoicing Tax Expense | Tax | NA |  |  |  | n/a | Finance | Ben Matters | Customer | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | When RMIT AUS is invoiced from RMIT Spain or Vietnam the tax amount charged hits the expense line - as such we need a new tax applicability, and a change in the APRs to post to expense. | This is required as current workday configuration can post to the expense however, this would cause an intercompany variance. | TRUE (must explain in Change Control justification) | High | n/a | n/a | n/a | n/a |  |  | Update test scripts | 2020-05-25 | 2020-05-25 |  | Phase 2 | SIT2 | 2020-05-19 | Workstream
164 | New Book Code: Lease Expense | Assets | SIT2 |  |  |  | Remapping of historical conversion logic | Finance | Hunter Pool |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | The addition of a new book code called lease Expense | In order to satisfy the requirements for the Maintain Lease Contract Book Code Configuration task, only one accounting method is allowed per book code | TRUE (must explain in Change Control justification) | High | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2020-05-25 | 2020-05-19 |  | Phase 2 | SIT1 | 2020-05-19 | Workstream
165 | Spend Category for financial budget to Level 3 | Finance | TBD |  |  | Mapping update for budget extract. May change in future based on analysis and poutput | data team need to map the data at correct spend category level | Finance | Omer Bilal |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | WD configuration file is showing that financials will be loaded on hierarchy 2 instead of hierarchy 3 for spend category | Business decision is to budget at spend category hierarchy Level 3 | High: High; NA: Reports will show data at SC level 3 instead if level 2 |  |  |  |  | Phase 2 |  | 2020-05-21
167 | Contract value check should not apply to catalogue contracts | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | NA | Procurement Ops |  | NA | Jen Kyle | Brad West | Configuration | Workday | NA | Pending Approval | A custom validation triggers to error a purchase when there is insufficient funds on a contract This should not apply for catalogue contracts. | There is no requirement for a purchase request to have a contract balance check and if insufficient to error. | FALSE | High | NA | NA | NA | NA | NA | NA | Test cases to be updated for SIT2 | 2020-06-01 |  |  | Phase 2 | SIT2 | 2020-05-25 | Workstream
168 | Authority Type and Signature Methods updated | Banking | NA |  |  |  | NA | Finance | Sarah Dozortseva |  | Natalia Hawkins | Aneta Wielgus | Configuration | Workday |  | Pending Approval | Signature methods changed from "2 signatories" to "2 x Group A" and "1 Group A & 1 Group B". These entries have been removed from the Authority Types Tab. | Changed to more clearly communicate bank account signatory records. | FALSE | Low | NA | NA | NA | NA | NA | NA | NA |  |  |  | Phase 2 | SIT1 | 2020-05-25 | Workstream
169 | Custom Validations updates to Requisition process | P2P (R2P2R, I2P, Supplier Record) | NA |  |  |  | nil | Procurement Ops |  | Finance | Jen Kyle | Brad West | Process | Workday |  |  | Addition of 2 custom validations to align PO Cvs with req CVs, including; enforcing 'donations claim form' to be attached when gift worktag is used. restricting users from transacting against the 'contingency' phase of the project | align PO requirements with requisition as all purchases will be through requisition | FALSE | Medium | nil | nil | nil | requirement from finance, to be implemented on Proc BP | nil | nil | Slight change to test cases to reflect updates |  |  |  | Phase 3 - Advanced HR | SIT1 | 2020-05-25 | Workstream |  | Finance and Procurement are both across requested change. No impact to additional streams