## Summary
Data Mapping & ETL Specifications | [5 empty] | Crosswalk |  |  |  | Crosswalk Status
Prototype | Total No. of Fields | Total No. of Mapped Fields | Mapping Completion (%) | Tech. Specs Completed | Tech Specs Completed (%) | Prototype | No. of Crosswalks | No. of Crosswalk Complete | Crosswalk Completion (%) | Crosswalk Status | No. of Crosswalk
P1 | 454 | 450 | 98.35% | 428 | 94.27% | P1 | 73 | 70 | 95.33% | Completed | 24
P2 | 258 | 53 | 29.02% | 3 | 1.163% | P2 | 1 | 1 | 100% | No Source | 7
Grand Total | 712 | 503 | 69.02% | 431 | 60.53% | Grand Total | 74 | 71 | 97.31% | Pending Workbook | 3
[10 empty] | Ready to Map | 32
[10 empty] | Grand Total | 66

## Crosswalk Tracker
Crosswalk Dashboard
Workday Configuration Crosswalk
Crosswalk File | Crosswalk | Status | In Functional Core HCM Workbook | In HR Mapping Specification | Comments
HCM Core Crosswalk | EMPLOYEE_TYPE | Completed | Yes | Yes
HCM Core Crosswalk | CONTINGENT_WORKER_TYPE | Completed | Yes | Yes
HCM Core Crosswalk | ORGANIZATION_SUBTYPE | No Source | Yes | Yes | To come from Snehal via Eric's landing table
HCM Core Crosswalk | LOCATION | Completed | Yes | Yes
HCM Core Crosswalk | JOB_PROFILE | Ready to Map | Yes | Yes
HCM Core Crosswalk | PAY_RATE_TYPE | Completed | Yes | Yes
HCM Core Crosswalk | PHONE_DEVICE_TYPE | Completed | Yes | Yes | KH completed on 5.8.2019
HCM Core Crosswalk | GENDER | Completed | Yes | Yes
HCM Core Crosswalk | DISABILITY | No Source | Yes | Yes | KH mapped on 7.8.2019
HCM Core Crosswalk | PASSPORT_TYPE | Completed | Yes | Yes
HCM Core Crosswalk | VISA_TYPE | Ready to Map | Yes | Yes | KH mapped on 7.8.2019
HCM Core Crosswalk | CUSTOM_ID_TYPE | Completed | Yes | Yes
HCM Core Crosswalk | EMERGENCY_CONTACT_RELATIONSHIP | No Source | Yes | Yes | No source, will default to Other
HCM Core Crosswalk | PAY_GROUP | Completed | Yes | Yes
HCM Core Crosswalk | ETHNICITIES | No Source | Yes | No | KH mapped on 7.8.2019
HCM Core Crosswalk | CITIZENSHIP_STATUS | No Source | Yes | No | Marked as not in scope in HR Mapping Spec
HCM Core Crosswalk | LICENSE_TYPE | No Source | Yes | No | Marked as not in scope in HR Mapping Spec
HCM Core Crosswalk | COLLECTIVE_AGREEMENT | Ready to Map | Yes | Yes | Pending Ken
HCM Core Crosswalk | NAME_COMPONENTS | Pending Workbook | Yes | Yes
HCM Core Crosswalk | COMM_USAGE_BEHAVIOUR | Completed | Yes | Yes | Address Type pending Kath (KH completed on 5.8.2019)
HCM Core Crosswalk | HIRE_REASON | Ready to Map | Yes | Yes
HCM Core Crosswalk | CONTRACT_CW_REASON | Ready to Map | Yes | Yes
HCM Core Crosswalk | TERMINATION_REASON | Pending Workbook | Yes | Yes | 3 GAPS
HCM Core Crosswalk | COMPANY | Completed | Yes | Yes
HCM Core Crosswalk | COST_CENTER | Ready to Map | Yes | Yes | Pending Thom email reply on using random assignment for just P1
HCM WDLOOKUP Crosswalk | WORKER_TYPE | Completed | Yes | Yes
HCM WDLOOKUP Crosswalk | POSITION_TIME_TYPE | Completed | Yes | Yes | Defaulted in Mapping Spec
HCM WDLOOKUP Crosswalk | BANK_ACCOUNT_TYPE | Completed | Yes | Yes
HCM WDLOOKUP Crosswalk | COMM_USAGE_TYPE | Completed | Yes | Yes | Defaulted in Mapping Spec
HCM WDLOOKUP Crosswalk | NATIONAL_ID_TYPE | Completed | Yes | Yes | Mark as not in scope of P1 in HR Mapping Spec
HCM WDLOOKUP Crosswalk | CURRENCY_CODE | Completed | Yes | Yes
HCM WDLOOKUP Crosswalk | COUNTRY_ISO_CODE | Ready to Map | Yes | Yes | Kath to finish today
HCM WDLOOKUP Crosswalk | COUNTRY_REGION | Completed | Yes | Yes
Pi_DTA_Workday_Recruiting_Crosswalk | CONTRACT_TYPE | Ready to Map | Yes | Yes | Pending Kath today
Pi_DTA_Workday_Recruiting_Crosswalk | CONTRACT_STATUS | Completed | Yes | Yes | Defaulted in Mapping Spec
Pi_DTA_Workday_Recruiting_Crosswalk | CONTRACT_REASON | Completed | Yes | Yes | Defaulted in Mapping Spec
Pi_DTA_Workday_Talent_And_Performance_Crosswalk | REVIEW_TEMPLATE | Ready to Map | Yes | Yes
Pi_DTA_Workday_Talent_And_Performance_Crosswalk | REVIEW_RATING | Ready to Map | Yes | Yes
Pi_DTA_Workday_Talent_And_Performance_Crosswalk | SCHOOL | Completed | Yes | Yes
Pi_DTA_Workday_Talent_And_Performance_Crosswalk | SCHOOL_TYPE | Completed | Yes | Yes
Pi_DTA_Workday_Talent_And_Performance_Crosswalk | DEGREE | Ready to Map | Yes | Yes | Leave to Ken
Pi_DTA_Workday_Talent_And_Performance_Crosswalk | DEGREE_COMPLETED | Completed | Yes | Yes | Default to Completed
Pi_DTA_Workday_Talent_And_Performance_Crosswalk | FIELD_OF_STUDY | Completed | Yes | Yes
Pi_DTA_Workday_Talent_And_Performance_Crosswalk | CERTIFICATION | No Source | Yes | Yes | Get bak to Hershi that we have nio data for this
Pi_DTA_Workday_Compensation_Crosswalk | COMPENSATION_FREQUENCY | Ready to Map | Yes | Yes
Pi_DTA_Workday_Compensation_Crosswalk | COMPENSATION_PACKAGE | Ready to Map | Yes | Yes
Pi_DTA_Workday_Compensation_Crosswalk | COMPENSATION_GRADE | Ready to Map | Yes | Yes
Pi_DTA_Workday_Compensation_Crosswalk | COMPENSATION_GRADE_PROFILE | Ready to Map | Yes | Yes
Pi_DTA_Workday_Compensation_Crosswalk | COMPENSATION_STEP | Ready to Map | Yes | Yes
Pi_DTA_Workday_Compensation_Crosswalk | PAY_PLAN | Ready to Map | Yes | Yes
Pi_DTA_Workday_Compensation_Crosswalk | ALLOWANCE_PLAN | Ready to Map | Yes | Yes
Pi_DTA_Workday_Compensation_Crosswalk | PERIOD_SALARY_PLAN | Ready to Map | Yes | Yes | Only for Vietnam
Pi_DTA_Workday_Benefits_Crosswalk | BENEFIT_PROVIDER | Ready to Map | Yes | Yes
Pi_DTA_Workday_Benefits_Crosswalk | HEALTH_CARE_COVERAGE_PLAN | Ready to Map | Yes | Yes
Pi_DTA_Workday_Benefits_Crosswalk | HEALTH_CARE_COVERAGE_TARGET | Ready to Map | Yes | Yes
Pi_DTA_Workday_Benefits_Crosswalk | INSURANCE_COVERAGE_PLAN | Pending Workbook | Yes | Yes | Incorrect IDs in config workbook
Pi_DTA_Workday_Benefits_Crosswalk | INSURANCE_COVERAGE_AMOUNT | Ready to Map | Yes | Yes
Pi_DTA_Workday_Benefits_Crosswalk | RETIREMENT_SAVINGS_PLAN | Ready to Map | Yes | Yes
Pi_DTA_Workday_Benefits_Crosswalk | ADDITIONAL_BENEFITS_PLAN | Ready to Map | Yes | Yes
Pi_DTA_Workday_Benefits_Crosswalk | ADDITIONAL_BENEFITS_COVERAGE_TARGET | Ready to Map | Yes | Yes
Pi_DTA_Workday_Absence_Crosswalk | TIME_OFF_TYPE | Ready to Map | Yes | Yes
Pi_DTA_Workday_Absence_Crosswalk | TIME_OFF_CODE | Ready to Map | Yes | Yes
Pi_DTA_Workday_Absence_Crosswalk | LEAVE_OF_ABSENCE_TYPE | Ready to Map | Yes | Yes
Pi_DTA_Workday_Absence_Crosswalk | LEAVE_REASON | Ready to Map | Yes | Yes
Pi_DTA_Workday_Absence_Crosswalk | ACCRUAL_CODE | Ready to Map | Yes | Yes
Pi_DTA_Workday_Absence_Crosswalk | WORK_SCHEDULE | Ready to Map | Yes | Yes

## P1 Dashboard
[11 empty] | Detailed Design | [11 empty] | Build |  |  |  |  | Load |  |  |  |  | Validation | [7 empty] | Build Resource
| Item No. | Order | File | Comments | Prototype | Load Method | Full/Delta | No. of Fields | Mapped Fields | Specs Completed | Target Workday Configuration Receival Date | Workday Configuration Received Date | Target Mapping Completion Date | Target Specification Completion Date | Mapping Completion % | Mapping Completion Date | Number of Crosswalk | Crosswalk Complete | Crosswalk Completion % | Specification Completion % | Specification Completion Date | Completion % | Target Build Completion Date | Transformation Build | Build Completion Date | Hoover Map Build | Hoover Scripts Build | Target Load Date | Load File Generated | Validated | Loaded | Data Loaded Date | Total Records | Total Pass | Total Failed | Pass Rate | Validation Complete | Reconciliation Complete | Testing Completion Date | Comments | Assigned To | Assigned On
| 1 | HR01 | SUPERVISORY_ORGANIZATIONS | 12/08: Semi automated. Eric created script to pul oRg structure from SAP and additional manual information are added. Enhanced data is manually maintained. Confirm with ERIC | P1 | Hoover | Full Load | 12 | 12 | 12 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-02 | 1 | 1 | 100% | 100% | 2019-08-02 | 100% | 4369800% | Complete | 4369800% | Complete | Complete | 4369800% | Yes | Yes | Yes | 4369800% | 0 | 0 | 0 | - | No | No |  |  |  | 4368900%
| 2 | HR02 | APPLICANTS |  | P1 | Hoover | Full Load | 12 | 12 | 12 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-02 | 1 | 1 | 100% | 100% | 2019-08-02 | 100% | 4369800% | Complete | 4369900% | Complete | Complete | 4369800% | Yes | Yes | Yes | 4369900% | 0 | 0 | 0 | - | No | No |  |  | Deepakkumar Tiwari | 4368900%
Overdue | 3 | HR03 | CREATE_POSITION | Need to revisit mapping post P1 Mapping is specific to P1 06/8 = Ken working through creating the hierarchy, Nitin and Tri to understand and agree on Specs. Only 1 unmapped field - Job Profile. Choose a default based on a Level 7/08: Need more information/ work in maping and identifying the proces to load job profiles. 08/08 - Additional complexity for mapping Training Job Profiles. Ken to speak with Eric about defaulting data for training for P1. 12/08: Defaulting for P1 (not ernough info in SAP). Job profile is expected to manually mapped and maintained throughput the project cycle by a Functional Team member | P1 | Hoover | Full Load | 11 | 11 | 10 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-09 | 5 | 5 | 100% | 90.91% | 2019-08-09 | 96.97% | 4370000% | In Progress |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  | Need to revisit mapping post P1 Mapping is specific to P1 06/8 = Ken working through creating the hierarchy, Nitin and Tri to understand and agree on Specs | Deepakkumar Tiwari | 4368900%
Overdue | 4 | HR04 | HIRE_EMPLOYEES | Need to revisit mapping post P1 Mapping is specific to P1 06/8 = Ken working through creating the hierarchy, Nitin and Tri to understand and agree on Specs. Only 1 unmapped field - Job Profile. Choose a default based on a Level 8/8 - Job profile pending - Same as CREATE_POSITION | P1 | Hoover | Full Load | 19 | 19 | 18 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-09 | 4 | 4 | 100% | 94.74% | 2019-08-09 | 98.25% | 4370000% | In Progress |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  | Need to revisit mapping post P1 Mapping is specific to P1 | Deepika Ghai | 4368900%
Overdue | 5 | HR05 | CONTRACT_CONTINGENT_WORKERS | Need to revisit mapping post P1 Mapping is specific to P1 06/8 = Ken working through creating the hierarchy, Nitin and Tri to understand and agree on Specs. Only 1 unmapped field - Job Profile. Choose a default based on a Level | P1 | Hoover | Full Load | 18 | 18 | 17 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-09 | 3 | 3 | 100% | 94.44% | 2019-08-09 | 98.15% | 4370000% | In Progress |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  |  | 4368900%
Overdue | 6 | HR07 | ASSIGN_MANAGERS | 12/08: Supervisory Org follows the same logic as HR-01 | P1 | Hoover | Full Load | 2 | 2 | 2 | 4366100% | 4366900% | 4367200% | 4368200% | 100% |  | 0 | 0 | 100% | 100% |  | 100% | 4370000% | In Progress |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  | Deepakkumar Tiwari | 4368900%
Overdue | 7 | HR08 | TERMINATE_EMPLOYEES |  | P1 | Hoover | Full Load | 6 | 6 | 6 | 4366100% | 4366900% | 4367200% | 4368200% | 100% |  | 1 | 1 | 100% | 100% |  | 100% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 8 | HR09 | SUPERVISORY_ORGANIZATION_DEFAULTS |  | P2 | Hoover | Full Load | 4 | 0 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 0% |  |  |  | 100% | 0% |  | 33.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 9 | HR10 | MAINTAIN_CONTACT_INFORMATION_PHONE | 7/8: Need Eric's inout. Tri to discuss with Eric. Eric to evaluate country code 12/08: TBC. RMIT Decided not to store corporate phone number in Workday HCM module.. | P1 | Hoover | Full Load | 10 | 10 | 10 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-06 | 2 | 2 | 100% | 100% | 2019-08-07 | 100% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  | Deepika Ghai | 4369700%
Overdue | 10 | HR11 | MAINTAIN_CONTACT_INFORMATION_EMAIL |  | P1 | Hoover | Full Load | 7 | 7 | 7 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-06 | 1 | 1 | 100% | 100% | 2019-08-07 | 100% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  | Deepika Ghai | 4369700%
Overdue | 11 | HR12 | MAINTAIN_CONTACT_INFORMATION_ADDRESS | Vietnam and Spain Crosswalk info pending Dependence on updated workbok Config Eric to update Vietnam Crosswalk | P1 | Hoover | Full Load | 38 | 38 | 38 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-02 | 3 | 3 | 100% | 100% |  | 100% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  | Deepika Ghai | 4369700%
Overdue | 12 | HR13 | CHANGE_LEGAL_NAME | Vietnam and Spain Crosswalk info pending Dependence on updated workbok Config Eric to update Vietnam Crosswalk | P1 | Hoover | Full Load | 18 | 18 | 18 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-07 | 3 | 3 | 100% | 100% | 2019-08-02 | 100% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  | Vietnam and Spain Crosswalk info pending Dependence on updated workbok Config Eric to update Vietnam Crosswalk | Deepakkumar Tiwari | 4369700%
Overdue | 13 | HR14 | CHANGE_PREFERRED_NAME | 8/8 Count of fields to be updated, 2 new fields added | P1 | Hoover | Full Load | 16 | 16 | 16 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-07 | 3 | 3 | 100% | 100% | 2019-08-02 | 100% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  | Vietnam and Spain Crosswalk info pending Dependence on updated workbok Config Eric to update Vietnam Crosswalk |  | 4369700%
Overdue | 14 | HR15 | CHANGE_PERSONAL_INFORMATION | SAP doesn’t have VISA number which is required if a VISA is to be entered at all. Ken was to follow up. 06/08: Need to check if a new function can be introduce in Legacy SAP system. For P1 - Finish the Type mapping and hardcode VISA number. 07/08: Can a BAU resource create a script to extract VISA related information from SAP. Beng to read and load the output. 8/8 - All fields mapped. Script for TEXT extraction in progress but not ready for P1 12/8: Decision. If the VISa number is not available in the text extract, the field will be dfaulted to "Not Available" | P1 | Hoover | Full Load | 30 | 30 | 30 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-02 | 4 | 4 | 100% | 100% | 2019-08-02 | 100% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  | Deepakkumar Tiwari | 4369700%
Overdue | 15 | HR16 | CHANGE_PASSPORTS_AND_VISAS | Moved date to 6/8 8/8 - Spec in progress, complex logic required | P1 | Hoover | Full Load | 12 | 12 | 12 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-07 | 5 | 5 | 100% | 100% | 2019-08-07 | 100% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  |  | 4369700%
Overdue | 16 | HR17 | CHANGE_OTHER_IDS | Ken to complete allowance mapping Moved date to 7/8 07/08: Compensation is out of scope for casuals in P1. Tri to confirm if Casual employee can accept $0 as Annual Salary in Workday 07/08: 2 Crosswlaks can be done tomorrow. 2 Crosswalk to be discessed between Ken and Tri 8/8 - 2 crosswalks pending. Allowance and Comp Grade Profile. Questions to be raised with functional team on grade profile 12/8: Gaps in Workday Config. Ken to folow up with Tom. | P1 | Hoover | Full Load | 7 | 7 | 5 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-06 | 2 | 2 | 100% | 71.43% | 2019-08-08 | 90.48% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  | Deepakkumar Tiwari | 4369700%
Overdue | 17 | HR18 | REQUEST_COMPENSATION_CHANGE | 1 xwalk pending Moved to tomorrow. Tri to raise with Micheal at 3 PM today for workbook 07/08: Vijay to check with Tri on the status of the workbook 12/08: Tri - SImon W has received confirmation for defaulting this to "PAYMENT_ELECTION_RULE-6-1". | P1 | Hoover | Full Load | 19 | 19 | 19 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-07 | 5 | 3 | 60% | 100% | 2019-08-08 | 86.67% | 4370000% | In Progress |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  | Configuration doesn't cater for Casual employees. Need to revisit in P2 | Deepika Ghai | 4368900%
Overdue | 18 | HR19 | PAYMENT_ELECTION_ENROLLMENT | moving date from 5/8 to tomorrow | P1 | Hoover | Full Load | 23 | 23 | 22 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-07 | 3 | 3 | 100% | 95.65% | 2019-08-08 | 98.55% | 4370000% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  |  | 4368900%
Overdue | 19 | HR20 | MATRIX_ORGANIZATION_ASSIGNMENT | SF mapping confirmation and file pending Snehal Ken and Kath to discuss with Snehal today and advice on the date 07/08: Kat to discuss with Tri and re map Mgr. Comments & Emp. Coments 8/8 - 2 comment fields pending, + SW to check with Eric/Beng on loading file to BODS | P2 | Hoover | Full Load | 3 | 1 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 33.33% |  |  |  | 100% | 0% |  | 44.44% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 20 | HR24 | MANAGE_LANGUAGES | 3 fields pending Kath/Ken 06/8 - Data Cleansing required for the mapped field. Split the name iinto first name and last name based on the "Space" in text. Some data will be missing space or missing last name 07/08: Maping complete based on above workaround. 12/08: Decision - As above | P2 | Hoover | Full Load | 9 | 3 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 33.33% |  |  |  | 100% | 0% |  | 44.44% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 21 | HR25 | MANAGE_EDUCATION | Date changed to 7/8 07/08: Kat finished the maping and Crosswlak. Ken to review and confirm. 08/08 - Ken/Kathleen to update HR-35-090 with collective agreement logic (ie which field to check first) | P1 | Hoover | Full Load | 18 | 18 | 18 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-07 | 6 | 6 | 100% | 100% | 2019-08-07 | 100% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  | Need to verify if correct set of data exists in SAP HR
| 22 | HR27 | MANAGE_CERTIFICATIONS |  | P2 | Hoover | Full Load | 12 | 2 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 16.67% |  |  |  | 100% | 0% |  | 38.89% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
| 23 | HR30 | EMPLOYEE_TIME_OFF_EVENTS |  | P2 | Hoover | Full Load | 7 | 6 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 85.71% |  |  |  | 100% | 0% |  | 61.9% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 24 | HR31 | EMPLOYEE_PERFORMANCE_REVIEWS | 6/8: Moved date from 02/8 to 7/8 07/08: Vijay to folow up with Tri and Simon 8/8 - SW to confirm benefit event ref ids today 12/08: Tri - Comment field mapped to SF just pending Kath to check and confirm. 13/08 - Tri: All Done but Eric raised that RMIT online has its own Performance Review system. Will this be in P1 scope? | P1 | Hoover | Full Load | 9 | 7 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 77.78% | 2019-08-09 | 2 | 2 | 100% | 0% | 2019-08-08 | 59.26% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 25 | HR32 | REQUEST_LEAVE_OF_ABSENCE | 1 field not yet mapped Decision: Cost Centre will be hardcoded to 5 cost centres for P1 07/08: Ken to work with Kat and derive Cost Centre 8/8 - Logic for which tables to use for Cost Centre and Company to be defined 12/08: Decision. Cost Centre wil be hardcoded to 4 in P1. | P2 | Hoover | Full Load | 8 | 5 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 62.5% |  |  |  | 100% | 0% |  | 54.17% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 26 | HR33 | REQUEST_RETURN_FROM_LEAVE_OF_ABSENCE |  | P2 | Hoover | Full Load | 4 | 2 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 50% |  |  |  | 100% | 0% |  | 50% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 27 | HR34 | EMPLOYEE_EMERGENCY_CONTACTS | Moved from 5/8 to 6/8 07/08: Kat finished the maping and Crosswlak. Ken to review and confirm. 08/08 - Ken/Kathleen to update HR-35-090 with collective agreement logic (ie which field to check first) | P1 | Hoover | Full Load | 74 | 74 | 73 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-07 | 5 | 5 | 100% | 98.65% | 2019-08-08 | 99.55% | 4371400% | Not Started |  | In Progress | In Progress |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 28 | HR35 | EMPLOYEE_CONTRACT |  | P1 | Hoover | Full Load | 17 | 17 | 15 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-07 | 2 | 2 | 100% | 88.24% |  | 96.08% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 29 | HR36 | EDIT_SERVICE_DATES | 07/08: Password can be hardcoded in P1. 12/08: Decision. Password generated in SSIS following RMIT poassword requirements | P1 | Hoover | Full Load | 3 | 3 | 2 | 4366100% | 4366900% | 4367200% | 4368200% | 100% |  | 0 | 0 | 100% | 66.67% | 2019-08-08 | 88.89% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  |  | 4369700%
Overdue | 30 | HR37 | DEPENDENTS | Dependency on Wendy to complete configuration 07/08: Ken to review Wendy's output and map , create croswalk 8/8 - Updated workbook from Wendy now available. Eric and Ken to work on logic to map. 12/8: Still pending with Wendy. | P2 | Hoover | Full Load | 34 | 7 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 20.59% |  |  |  | 100% | 0% |  | 40.2% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
| 31 | HR38 | CREATE_NAMED_PROFESSORSHIP |  | P2 | Hoover | Full Load | 11 | 0 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 0% |  |  |  | 100% | 0% |  | 33.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 32 | HR40 | CHANGE_GOVERNMENT_IDS |  | P1 | Hoover | Full Load | 16 | 16 | 16 | 4366100% | 4366900% | 4367200% | 4368200% | 100% |  | 1 | 1 | 100% | 100% |  | 100% | 4370700% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  |  | 4369700%
Overdue | 33 | HR41 | CHANGE_BENEFITS_FOR_LIFE_EVENT | 6/8: Moved date from 02/8 to 7/8 07/08: Vijay to folow up with Tri and Simon 8/8 - SW to confirm benefit event ref ids today | P1 | Hoover | Full Load | 14 | 13 | 11 | 4366100% | 4366900% | 4367200% | 4368200% | 92.86% | 2019-08-08 | 4 | 4 | 100% | 78.57% | 2019-08-09 | 90.48% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 34 | HR42 | CARRYOVER_BALANCES |  | P2 | Hoover | Full Load | 9 | 5 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 55.56% |  |  |  | 100% | 0% |  | 51.85% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 35 | HR43 | ACCRUAL_OVERRIDES |  | P2 | Hoover | Full Load | 8 | 5 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 62.5% |  |  |  | 100% | 0% |  | 54.17% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 36 | HR44 | BENEFICIARIES |  | P2 | Hoover | Full Load | 32 | 4 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 12.5% |  |  |  | 100% | 0% |  | 37.5% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 37 | HR45 | ASSIGN_ORGANIZATIONS | 1 field not yet mapped Decision: Cost Centre will be hardcoded to 5 cost centres for P1 07/08: Ken to work with Kat and derive Cost Centre 8/8 - Logic for which tables to use for Cost Centre and Company to be defined 12/8 - Tri: As explained to Nitin, mapping is completed. | P1 | Hoover | Full Load | 6 | 6 | 4 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-09 | 2 | 2 | 100% | 66.67% | 2019-08-09 | 88.89% | 4370000% | In Progress |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  |  | 4368900%
Overdue | 38 | HR46 | ASSIGN_EMPLOYEES_TO_PAY_GROUP |  | P1 | Hoover | Full Load | 4 | 4 | 4 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-02 | 1 | 1 | 100% | 100% | 2019-08-05 | 100% | 4370000% | In Progress |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  |  |  | 4368900%
Overdue | 39 | HR47 | ADD_RETIREE_STATUS |  | P2 | Hoover | Full Load | 4 | 3 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 75% |  |  |  | 100% | 0% |  | 58.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 40 | HR49 | EMPLOYEE_COLLECTIVE_AGREEMENTS | Moved from 5/8 to 6/8 07/08: Kat finished the maping and Crosswlak. Ken to review and confirm. 08/08 - Ken/Kathleen to update HR-35-090 with collective agreement logic (ie which field to check first) | P1 | Hoover | Full Load | 15 | 15 | 14 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-09 | 1 | 1 | 100% | 93.33% | 2019-08-09 | 97.78% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 41 | HR50 | CUSTOM_FIELDS |  | P2 | Hoover | Full Load | 5 | 3 | 3 | 4366100% | 4366900% | 4367200% | 4368200% | 60% |  | 1 | 1 | 100% | 60% |  | 73.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 42 | HR51 | EMPLOYEE_NOTICE_PERIOD |  | P1 | Hoover | Full Load | 7 | 7 | 7 | 4366100% | 4366900% | 4367200% | 4368200% | 100% |  | 1 | 1 | 100% | 100% | 2019-08-07 | 100% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 43 | HR52 | COSTING_ALLOCATION |  | P2 | Hoover | Full Load | 16 | 6 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 37.5% |  |  |  | 100% | 0% |  | 45.83% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 44 | HR53 | ADD_ACADEMIC_APPOINTMENTS |  | P2 | Hoover | Full Load | 22 | 0 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 0% |  |  |  | 100% | 0% |  | 33.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 45 | HR54 | TALENT_POOLS |  | P2 | Hoover | Full Load | 8 | 0 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 0% |  |  |  | 100% | 0% |  | 33.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 46 | HR56 | MANAGE_SUCCESSION_PLANS |  | P2 | Hoover | Full Load | 6 | 0 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 0% |  |  |  | 100% | 0% |  | 33.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 47 | HR58 | CREATE_JOB_REQUISITIONS |  | P2 | Hoover | Full Load | 29 | 0 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 0% |  |  |  | 100% | 0% |  | 33.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
| 48 | HR59 | CREATE_EVERGREEN_REQUISITION |  | P2 | Hoover | Full Load | 21 | 0 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 0% |  |  |  | 100% | 0% |  | 33.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 49 | HR60 | ASSIGN_PRIMARY_RECRUITER |  | P2 | Hoover | Full Load | 3 | 0 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 0% |  |  |  | 100% | 0% |  | 33.33% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 50 | HR61 | EMPLOYEE_TRAVEL_PROFILE |  | P2 | Hoover | Full Load | 3 | 1 | 0 | 4366100% | 4366900% | 4367200% | 4368200% | 33.33% |  |  |  | 100% | 0% |  | 44.44% | 4375000% | Not Started |  |  |  |  | No | No | No |  | 0 | 0 | 0 | - | No | No
Overdue | 51 | HR62 | ADD_WORKDAY_ACCOUNT | 07/08: Password can be hardcoded in P1. | P1 | Hoover | Full Load | 6 | 6 | 6 | 4366100% | 4366900% | 4367200% | 4368200% | 100% | 2019-08-02 | 1 | 1 | 100% | 100% | 2019-08-07 | 100% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No
| 52 | HR67 | ASSIGN_WORK_SCHEDULE | Dependency on Wendy to complete configuration 07/08: Ken to review Wendy's output and map , create croswalk 8/8 - Updated workbook from Wendy now available. Eric and Ken to work on logic to map. | P1 | Hoover | Full Load | 5 | 4 | 4 | 4366100% | 4366900% | 4367200% | 4368200% | 80% | 2019-08-09 | 1 | 0 | 0% | 80% | 2019-08-12 | 53.33% | 4371400% | Not Started |  | Complete | Complete |  | No | No | No |  | 0 | 0 | 0 | - | No | No |  | Decisions on work schedule are yet to be made (02/08)
[17 empty] | 74 | 71
Note on P37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 100% mapped but no SF file to confirm

## Sheet2 (hidden)
Status | xwalk_yn | xwalkstatus
Not Started | Yes | Pending Workbook
In Progress | No | Completed
Complete |  | Ready to be Map
No Source
Moved to HR Mapping Spec